## LTP 21-Sep-26
[6 empty] | Pending Effort (in Hours) |  |  |  | 21-Sep-2026 :: Addressing Plan | [10 empty] | 14-Sep-2026 :: Addressing Plan | [12 empty] | Verification
Market | DR | BR_ID | BR_Name | Driven Km | Drive Details | Source Prep | HLA | ADC | MPRA | Naming QA Acceptance | Source Prep Start Date | Source Prep End Date | HLA Start date | HLA End Date | ADC Start Date | ADC End Date | DC2 | Building Delivery Date | MPRA Start Date | MPRA End Date | Naming QA Acceptance | Source Prep Start Date | Source Prep End Date | HLA Start date | HLA End Date | ADC Start Date | ADC End Date | DC2 | Building Delivery Date | MPRA Start Date | MPRA End Date | Holiday List |  | Naming QA Acceptance | Source Prep Start Date | Source Prep End Date | HLA Start date | HLA End Date | ADC Start Date | ADC End Date | DC2 | Building Delivery Date | MPRA Start Date | MPRA End Date
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_A | São Paulo | 34714 | Post-drive |  |  |  | 100 | 2025-12-31 | - | - | 2026-01-06 | 2026-01-09 | 2026-01-10 | 2026-02-26 | 2026-06-20 | Available | 2026-06-22 | 2026-09-23 | 2025-12-31 | - | - | 2026-01-06 | 2026-01-09 | 2026-01-10 | 2026-02-26 | 2026-06-20 | Available | 2026-06-22 | 2026-09-23 | 2026-01-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_C | Campinas | 23453 | Post-drive |  |  |  | 8864 | 2026-01-07 | - | - | 2026-01-09 | 2026-01-12 | 2026-01-21 | 2026-02-11 | 2026-08-09 | Available | 2026-08-29 | 2026-10-25 | 2026-01-07 | - | - | 2026-01-09 | 2026-01-12 | 2026-01-21 | 2026-02-11 | 2026-08-09 | Available | 2026-08-29 | 2026-10-25 | 2026-01-14 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_D | Ribeirão Preto | 23151 | Post-drive |  |  |  | 14181 | 2026-01-19 | - | - | 2026-01-25 | 2026-01-29 | 2026-01-30 | 2026-02-28 | 2026-09-06 | Available | 2026-10-03 | 2026-11-22 | 2026-01-19 | - | - | 2026-01-25 | 2026-01-29 | 2026-01-30 | 2026-02-28 | 2026-09-06 | Available | 2026-09-15 | 2026-11-22 | 2026-01-26 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_B | São José dos Campos | 26018 | Post-drive |  |  |  | 14977 | 2026-01-27 | - | - | 2026-02-03 | 2026-02-07 | 2026-02-15 | 2026-03-12 | 2026-09-18 | Available | 2026-10-05 | 2026-11-27 | 2026-01-27 | - | - | 2026-02-03 | 2026-02-07 | 2026-02-15 | 2026-03-12 | 2026-09-18 | Available | 2026-09-19 | 2026-11-27 | 2026-04-03 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_A | Rio de Janeiro | 14299 | Post-drive |  |  |  | 3816.1 | 2026-01-29 | - | - | 2026-02-06 | 2026-02-19 | 2026-02-28 | 2026-03-24 | 2026-07-07 | Available | 2026-08-11 | 2026-09-28 | 2026-01-29 | - | - | 2026-02-06 | 2026-02-19 | 2026-02-28 | 2026-03-24 | 2026-07-07 | Available | 2026-08-11 | 2026-09-28 | 2026-05-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_B | Campos dos Goytacazes | 18163 | Post-drive |  |  |  | 8329 | 2026-01-31 | - | - | 2026-02-19 | 2026-02-21 | 2026-03-01 | 2026-03-26 | 2026-07-12 | Available | 2026-07-19 | 2026-10-12 | 2026-01-31 | - | - | 2026-02-19 | 2026-02-21 | 2026-03-01 | 2026-03-26 | 2026-07-12 | Available | 2026-07-19 | 2026-10-12 | 2026-05-27 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_C | Vitória | 7469 | Post-drive |  |  |  | 4314 | 2026-02-06 | - | - | 2026-02-25 | 2026-02-26 | 2026-03-09 | 2026-03-30 | 2026-07-21 | Available | 2026-08-13 | 2026-10-06 | 2026-02-06 | - | - | 2026-02-25 | 2026-02-26 | 2026-03-09 | 2026-03-30 | 2026-07-21 | Available | 2026-08-13 | 2026-10-06 | 2026-06-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.16 | Salvador | 23933 | Full-drive |  |  |  | 11303 | 2026-02-22 | 2024-11-11 | 2024-12-01 | 2026-03-11 | 2026-03-24 | 2026-03-26 | 2026-04-01 | 2026-10-04 | Available | 2026-10-08 | 2026-12-13 | 2026-02-22 | 2024-11-11 | 2024-12-01 | 2026-03-11 | 2026-03-24 | 2026-03-26 | 2026-04-01 | 2026-10-04 | Available | 2026-10-05 | 2026-12-13 | 2026-08-15 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.17 | Recife | 22668 | Full-drive |  |  |  | 7608 | 2026-03-10 | 2024-11-18 | 2024-12-01 | 2026-03-21 | 2026-03-26 | 2026-03-26 | 2026-05-26 | 2026-10-12 | Available | 2026-11-10 | 2026-12-22 | 2026-03-10 | 2024-11-18 | 2024-12-01 | 2026-03-21 | 2026-03-26 | 2026-03-26 | 2026-05-26 | 2026-10-12 | Available | 2026-11-10 | 2026-12-22 | 2026-09-14 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.18 | Natal | 14335 | Post-drive |  |  |  | 4263 | 2026-04-02 | - | - | 2026-04-04 | 2026-04-05 | 2026-04-09 | 2026-04-26 | 2026-10-21 | Available | 2026-11-15 | 2026-12-28 | 2026-04-02 | - | - | 2026-04-04 | 2026-04-05 | 2026-04-09 | 2026-04-26 | 2026-10-21 | Available | 2026-11-15 | 2026-12-28 | 2026-10-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.13 | Sao Luis | 11777 | Full-drive |  |  |  | 2286 | 2026-03-23 | 2025-01-06 | 2025-01-22 | 2026-04-06 | 2026-04-08 | 2026-04-16 | 2026-04-29 | 2026-10-25 | Available | 2026-11-18 | 2027-01-02 | 2026-03-23 | 2025-01-06 | 2025-01-22 | 2026-04-06 | 2026-04-08 | 2026-04-16 | 2026-04-29 | 2026-10-25 | Available | 2026-11-18 | 2027-01-02 | 2026-10-20 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.14 | Teresina | 8173 | Full-drive |  |  |  | 1748 | 2026-03-24 | 2025-01-09 | 2025-01-30 | 2026-04-11 | 2026-04-12 | 2026-04-15 | 2026-04-24 | 2026-10-28 | Available | 2026-11-21 | 2027-01-05 | 2026-03-24 | 2025-01-09 | 2025-01-30 | 2026-04-11 | 2026-04-12 | 2026-04-15 | 2026-04-24 | 2026-10-28 | Available | 2026-11-21 | 2027-01-05 | 2026-11-09 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.15 | Fortaleza | 15472 | Full-drive |  |  |  | 4370 | 2026-04-23 | 2024-12-06 | 2024-12-30 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-26 | 2026-11-07 | Available | 2026-11-29 | 2027-01-13 | 2026-04-23 | 2024-12-06 | 2024-12-30 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-26 | 2026-11-07 | Available | 2026-11-29 | 2027-01-13 | 2026-12-25 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.12 | Palmas | 6544 | Full-drive |  |  |  | 869 | 2026-05-06 | 2025-01-10 | 2025-01-31 | 2026-05-07 | 2026-05-09 | 2026-05-13 | 2026-05-30 | 2026-11-12 | Available | 2026-12-07 | 2027-01-21 | 2026-05-06 | 2025-01-10 | 2025-01-31 | 2026-05-07 | 2026-05-09 | 2026-05-13 | 2026-05-30 | 2026-11-12 | Available | 2026-12-07 | 2027-01-21 | 2027-01-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.10_B | Uberlândia | 24034 | Post-drive |  |  |  | 20596 | 2026-03-17 | - | - | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2026-04-28 | 2026-11-28 | Available | 2027-01-27 | 2027-02-28 | 2026-03-17 | - | - | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2026-04-28 | 2026-11-28 | Available | 2027-01-27 | 2027-02-28 | 2027-01-14 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.10_A | Belo Horizonte | 18327 | Post-drive |  |  |  | 10270 | 2026-05-13 | - | - | 2026-05-15 | 2026-05-18 | 2026-05-18 | 2026-06-27 | 2026-12-13 | Available | 2027-02-08 | 2027-03-25 | 2026-05-13 | - | - | 2026-05-15 | 2026-05-18 | 2026-05-18 | 2026-06-27 | 2026-12-13 | Available | 2027-02-08 | 2027-03-25 | 2027-01-26 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.09_B | Goiânia | 27365 | Full-drive |  |  |  | 10049 | 2026-06-28 | 2025-01-20 | 2025-02-01 | 2026-07-26 | 2026-07-30 | 2026-08-13 | 2026-08-31 | 2026-12-27 | Available | 2027-02-21 | 2027-04-07 | 2026-06-28 | 2025-01-20 | 2025-02-01 | 2026-07-26 | 2026-07-30 | 2026-08-13 | 2026-08-31 | 2026-12-27 | Available | 2027-02-21 | 2027-04-07 | 2027-04-03 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.09_A | Brasília | 8952 | Full-drive |  |  |  | 4111 | 2026-07-09 | 2024-12-28 | 2024-12-31 | 2026-07-11 | 2026-07-17 | 2026-07-20 | 2026-08-25 | 2027-01-02 | Available | 2027-03-03 | 2027-04-17 | 2026-07-09 | 2024-12-28 | 2024-12-31 | 2026-07-11 | 2026-07-17 | 2026-07-20 | 2026-08-25 | 2027-01-02 | Available | 2027-03-03 | 2027-04-17 | 2027-05-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.07_A | Curitiba | 28875 | Post-drive |  | 649 | 8884 | 14772 | 2026-10-17 | - | - | 2026-10-18 | 2026-11-01 | 2026-11-02 | 2026-11-23 | 2027-01-17 | Available | 2027-03-19 | 2027-05-03 | 2026-10-17 | - | - | 2026-10-18 | 2026-11-01 | 2026-11-02 | 2026-11-23 | 2027-01-17 | Available | 2027-03-19 | 2027-05-03 | 2027-05-27 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.06 | Porto Alegre | 24358 | Full-drive |  |  | 8576 | 14356 | 2026-07-30 | 2025-01-12 | 2025-01-31 | 2026-08-14 | 2026-08-24 | 2026-10-10 | 2026-10-28 | 2027-01-27 | Available | 2027-04-02 | 2027-05-12 | 2026-07-30 | 2025-01-12 | 2025-01-31 | 2026-08-14 | 2026-08-24 | 2026-10-10 | 2026-10-28 | 2027-01-27 | Available | 2027-04-02 | 2027-05-12 | 2027-06-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.05 | Corumba | 12741 | Post-drive |  |  |  | 4124 | 2026-08-11 | - | - | 2026-08-13 | 2026-08-14 | 2026-09-10 | 2026-09-20 | 2027-02-01 | Available | 2027-04-10 | 2027-05-17 | 2026-08-11 | - | - | 2026-08-13 | 2026-08-14 | 2026-09-10 | 2026-09-28 | 2027-02-01 | Available | 2027-04-10 | 2027-05-17 | 2027-08-15 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.07_B | Joinville | 16540 | Full-drive |  | 1845 | 5490 | 8436 | 2026-11-24 | 2025-02-01 | 2025-02-10 | 2026-11-25 | 2026-12-16 | 2026-12-17 | 2027-01-16 | 2027-02-09 | Available | 2027-04-20 | 2027-05-25 | 2026-11-24 | 2025-02-01 | 2025-02-10 | 2026-11-25 | 2026-12-16 | 2026-12-17 | 2027-01-16 | 2027-02-09 | Available | 2027-04-20 | 2027-05-25 | 2027-09-14 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.04 | Cuiaba | 13464 | Post-drive |  |  | 2508 | 6545 | 2026-08-19 | - | - | 2026-08-25 | 2026-08-28 | 2026-10-12 | 2026-10-30 | 2027-02-16 | Available | 2027-04-30 | 2027-05-31 | 2026-08-19 | - | - | 2026-08-25 | 2026-08-28 | 2026-10-12 | 2026-10-30 | 2027-02-16 | Available | 2027-04-30 | 2027-05-31 | 2027-10-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.01 | Porto Velho | 5848 | Zero-drive |  |  |  | 2920 | 2026-08-25 | 2024-11-06 | 2024-11-08 | 2026-08-26 | 2026-08-29 | 2026-09-16 | 2026-09-19 | 2027-02-17 | Available | 2027-05-05 | 2027-06-04 | 2026-08-25 | 2024-11-06 | 2024-11-08 | 2026-08-26 | 2026-08-29 | 2026-09-15 | 2026-09-30 | 2027-02-17 | Available | 2027-05-05 | 2027-06-04 | 2027-10-20 | Holiday | 0 | 0 | 0 | 0 | 0 | 1 | -11 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.03 | Belem | 8948 | Zero-drive |  | 2408 | 718 | 5554 | 2026-09-07 | 2024-11-08 | 2024-11-18 | 2026-09-17 | 2026-10-01 | 2026-10-05 | 2026-10-26 | 2027-02-19 | Available | 2027-05-11 | 2027-06-06 | 2026-09-07 | 2024-11-08 | 2024-11-18 | 2026-09-15 | 2026-10-01 | 2026-10-05 | 2026-10-26 | 2027-02-19 | Available | 2027-05-11 | 2027-06-06 | 2027-11-09 | Holiday | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.02 | Manaus | 13424 | Post-drive |  | 226 | 318 | 3840 | 2026-09-11 | - | - | 2026-09-17 | 2026-10-04 | 2026-10-07 | 2026-10-31 | 2027-02-19 | Available | 2027-05-16 | 2027-06-08 | 2026-09-11 | - | - | 2026-09-15 | 2026-10-04 | 2026-10-07 | 2026-10-31 | 2027-02-19 | Available | 2027-05-16 | 2027-06-08 | 2027-12-25 | Holiday | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSM | kh.br.as.idn.01 | Aceh | 7632.6119 | FD | 237 | 676 | 843 | 608 | 2027-07-26 | 2027-07-11 | 2027-07-21 | 2027-07-27 | 2027-08-10 | 2027-08-11 | 2027-09-05 | 2027-11-28 | Not Available | 2027-11-29 | 2027-12-14 | 2027-07-26 | 2027-07-11 | 2027-07-21 | 2027-07-27 | 2027-08-10 | 2027-08-11 | 2027-09-05 | 2027-11-28 | Not Available | 2027-11-29 | 2027-12-14 | 2028-01-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSM | kh.br.as.idn.05 | Lampung | 11419.8559 | FD | 405 | 1155 | 1441 | 1037 | 2027-08-28 | 2027-08-13 | 2027-08-23 | 2027-08-29 | 2027-09-12 | 2027-09-13 | 2027-10-08 | 2027-12-18 | Not Available | 2027-12-19 | 2028-01-10 | 2027-08-28 | 2027-08-13 | 2027-08-23 | 2027-08-29 | 2027-09-12 | 2027-09-13 | 2027-10-08 | 2027-12-18 | Not Available | 2027-12-19 | 2028-01-10 | 2028-01-26 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSM | kh.br.as.idn.04 | Sumatra Island South | 21126.6364 | FD | 697 | 1985 | 2478 | 1781 | 2027-09-09 | 2027-08-25 | 2027-09-04 | 2027-09-10 | 2027-09-24 | 2027-09-25 | 2027-10-19 | 2028-01-02 | Not Available | 2028-01-04 | 2028-01-25 | 2027-09-09 | 2027-08-25 | 2027-09-04 | 2027-09-10 | 2027-09-24 | 2027-09-25 | 2027-10-19 | 2028-01-02 | Not Available | 2028-01-04 | 2028-01-25 | 2028-04-03 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSM | kh.br.as.idn.03 | Sumatra Island Central | 20891.2863 | FD | 630 | 1793 | 2239 | 1611 | 2027-09-21 | 2027-09-06 | 2027-09-16 | 2027-09-22 | 2027-10-06 | 2027-10-07 | 2027-11-01 | 2028-01-14 | Not Available | 2028-01-16 | 2028-02-07 | 2027-09-21 | 2027-09-06 | 2027-09-16 | 2027-09-22 | 2027-10-06 | 2027-10-07 | 2027-11-01 | 2028-01-14 | Not Available | 2028-01-16 | 2028-02-07 | 2028-05-01 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSM | kh.br.as.idn.02 | Medan | 17053.2041 | FD | 666 | 1897 | 2368 | 1704 | 2027-09-29 | 2027-09-15 | 2027-09-24 | 2027-09-30 | 2027-10-14 | 2027-10-15 | 2027-11-08 | 2028-01-28 | Not Available | 2028-01-29 | 2028-02-20 | 2027-09-29 | 2027-09-15 | 2027-09-24 | 2027-09-30 | 2027-10-14 | 2027-10-15 | 2027-11-08 | 2028-01-28 | Not Available | 2028-01-29 | 2028-02-20 | 2028-05-27 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRKA | kh.br.as.idn.07 | West Kalimantan | 24285.3839 | FD | 364 | 1036 | 1293 | 931 | 2027-10-03 | 2027-09-18 | 2027-09-28 | 2027-10-04 | 2027-10-18 | 2027-10-19 | 2027-11-13 | 2028-02-11 | Not Available | 2028-02-12 | 2028-03-05 | 2027-10-03 | 2027-09-18 | 2027-09-28 | 2027-10-04 | 2027-10-18 | 2027-10-19 | 2027-11-13 | 2028-02-11 | Not Available | 2028-02-12 | 2028-03-05 | 2028-06-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRKA | kh.br.as.idn.06 | East Kalimantan | 19072.7125 | FD | 384 | 1095 | 1367 | 983 | 2027-10-06 | 2027-09-21 | 2027-10-01 | 2027-10-07 | 2027-10-21 | 2027-10-22 | 2027-11-16 | 2028-02-22 | Not Available | 2028-02-23 | 2028-03-16 | 2027-10-06 | 2027-09-21 | 2027-10-01 | 2027-10-07 | 2027-10-21 | 2027-10-22 | 2027-11-16 | 2028-02-22 | Not Available | 2028-02-23 | 2028-03-16 | 2028-08-15 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.09 | Jakarta | 3670.6587 | FD | 475 | 1354 | 1690 | 1217 | 2027-10-14 | 2027-09-29 | 2027-10-09 | 2027-10-15 | 2027-10-29 | 2027-10-30 | 2027-11-24 | 2028-03-03 | Not Available | 2028-03-04 | 2028-03-26 | 2027-10-14 | 2027-09-29 | 2027-10-09 | 2027-10-15 | 2027-10-29 | 2027-10-30 | 2027-11-24 | 2028-03-03 | Not Available | 2028-03-04 | 2028-03-26 | 2028-10-02 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.08 | Banten | 7393.3955 | FD | 536 | 1526 | 1904 | 1373 | 2027-10-24 | 2027-10-09 | 2027-10-19 | 2027-10-25 | 2027-11-08 | 2027-11-10 | 2027-12-04 | 2028-03-23 | Not Available | 2028-03-24 | 2028-04-15 | 2027-10-24 | 2027-10-09 | 2027-10-19 | 2027-10-25 | 2027-11-08 | 2027-11-10 | 2027-12-04 | 2028-03-23 | Not Available | 2028-03-24 | 2028-04-15 | 2028-10-20 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.10_A | West Java A | 11005.7701 | FD | 777 | 2212 | 2760 | 1988 | 2027-11-12 | 2027-10-28 | 2027-11-07 | 2027-11-13 | 2027-11-27 | 2027-11-28 | 2027-12-23 | 2028-04-08 | Not Available | 2028-04-09 | 2028-05-01 | 2027-11-12 | 2027-10-28 | 2027-11-07 | 2027-11-13 | 2027-11-27 | 2027-11-28 | 2027-12-23 | 2028-04-08 | Not Available | 2028-04-09 | 2028-05-01 | 2028-11-09 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.12_C | East Java C | 13706.3789 | FD | 632 | 1799 | 2245 | 1616 | 2027-11-29 | 2027-11-14 | 2027-11-24 | 2027-11-30 | 2027-12-14 | 2027-12-15 | 2028-01-09 | 2028-04-24 | Not Available | 2028-04-25 | 2028-05-17 | 2027-11-29 | 2027-11-14 | 2027-11-24 | 2027-11-30 | 2027-12-14 | 2027-12-15 | 2028-01-09 | 2028-04-24 | Not Available | 2028-04-25 | 2028-05-17 | 2028-12-25 | Holiday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.11_C | Yogyakarta | 13092.8417 | FD | 483 | 1375 | 1715 | 1234 | 2027-12-17 | 2027-12-02 | 2027-12-12 | 2027-12-18 | 2028-01-02 | 2028-01-03 | 2028-01-27 | 2028-05-07 | Not Available | 2028-05-09 | 2028-05-30 | 2027-12-17 | 2027-12-02 | 2027-12-12 | 2027-12-18 | 2028-01-02 | 2028-01-03 | 2028-01-27 | 2028-05-07 | Not Available | 2028-05-09 | 2028-05-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.12_B | East Java B | 11238.8128 | FD | 625 | 1781 | 2222 | 1601 | 2028-01-07 | 2027-12-23 | 2028-01-02 | 2028-01-08 | 2028-01-22 | 2028-01-23 | 2028-02-17 | 2028-05-18 | Not Available | 2028-05-19 | 2028-06-10 | 2028-01-07 | 2027-12-23 | 2028-01-02 | 2028-01-08 | 2028-01-22 | 2028-01-23 | 2028-02-17 | 2028-05-18 | Not Available | 2028-05-19 | 2028-06-10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.11_B | Central Java B | 9545.187 | FD | 509 | 1449 | 1810 | 1302 | 2028-01-23 | 2028-01-08 | 2028-01-18 | 2028-01-24 | 2028-02-07 | 2028-02-08 | 2028-03-04 | 2028-05-28 | Not Available | 2028-05-29 | 2028-06-20 | 2028-01-23 | 2028-01-08 | 2028-01-18 | 2028-01-24 | 2028-02-07 | 2028-02-08 | 2028-03-04 | 2028-05-28 | Not Available | 2028-05-29 | 2028-06-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.12_A | East Java A | 11006.766 | FD | 573 | 1632 | 2038 | 1466 | 2028-02-08 | 2028-01-24 | 2028-02-03 | 2028-02-09 | 2028-02-23 | 2028-02-24 | 2028-03-20 | 2028-06-10 | Not Available | 2028-06-11 | 2028-07-03 | 2028-02-08 | 2028-01-24 | 2028-02-03 | 2028-02-09 | 2028-02-23 | 2028-02-24 | 2028-03-20 | 2028-06-10 | Not Available | 2028-06-11 | 2028-07-03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.10_C | West Java C | 9856.5905 | FD | 627 | 1786 | 2229 | 1604 | 2028-02-22 | 2028-02-07 | 2028-02-17 | 2028-02-23 | 2028-03-08 | 2028-03-09 | 2028-04-03 | 2028-06-20 | Not Available | 2028-06-21 | 2028-07-13 | 2028-02-22 | 2028-02-07 | 2028-02-17 | 2028-02-23 | 2028-03-08 | 2028-03-09 | 2028-04-03 | 2028-06-20 | Not Available | 2028-06-21 | 2028-07-13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.10_B | West Java B | 9493.5621 | FD | 769 | 2190 | 2733 | 1968 | 2028-03-08 | 2028-02-22 | 2028-03-03 | 2028-03-09 | 2028-03-23 | 2028-03-24 | 2028-04-18 | 2028-06-30 | Not Available | 2028-07-01 | 2028-07-23 | 2028-03-08 | 2028-02-22 | 2028-03-03 | 2028-03-09 | 2028-03-23 | 2028-03-24 | 2028-04-18 | 2028-06-30 | Not Available | 2028-07-01 | 2028-07-23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRJW | kh.br.as.idn.11_A | Central Java A | 8464.8366 | FD | 652 | 1858 | 2318 | 1669 | 2028-03-23 | 2028-03-08 | 2028-03-18 | 2028-03-24 | 2028-04-07 | 2028-04-08 | 2028-05-03 | 2028-07-09 | Not Available | 2028-07-10 | 2028-08-01 | 2028-03-23 | 2028-03-08 | 2028-03-18 | 2028-03-24 | 2028-04-07 | 2028-04-08 | 2028-05-03 | 2028-07-09 | Not Available | 2028-07-10 | 2028-08-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSL | kh.br.as.idn.14 | Celebes South | 19403.9646 | FD | 590 | 1681 | 2097 | 1510 | 2028-04-07 | 2028-03-23 | 2028-04-02 | 2028-04-08 | 2028-04-22 | 2028-04-23 | 2028-05-18 | 2028-07-21 | Not Available | 2028-07-22 | 2028-08-12 | 2028-04-07 | 2028-03-23 | 2028-04-02 | 2028-04-08 | 2028-04-22 | 2028-04-23 | 2028-05-18 | 2028-07-21 | Not Available | 2028-07-22 | 2028-08-12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRSL | kh.br.as.idn.13 | Celebes North | 9176.757 | FD | 305 | 869 | 1084 | 781 | 2028-04-11 | 2028-03-27 | 2028-04-06 | 2028-04-12 | 2028-04-26 | 2028-04-27 | 2028-05-22 | 2028-07-24 | Not Available | 2028-07-25 | 2028-08-16 | 2028-04-11 | 2028-03-27 | 2028-04-06 | 2028-04-12 | 2028-04-26 | 2028-04-27 | 2028-05-22 | 2028-07-24 | Not Available | 2028-07-25 | 2028-08-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRNU | kh.br.as.idn.16 | East Nusa Tenggara | 10516.7618 | FD | 240 | 683 | 852 | 615 | 2028-04-17 | 2028-04-02 | 2028-04-12 | 2028-04-18 | 2028-05-02 | 2028-05-03 | 2028-05-28 | 2028-07-29 | Not Available | 2028-07-30 | 2028-08-21 | 2028-04-17 | 2028-04-02 | 2028-04-12 | 2028-04-18 | 2028-05-02 | 2028-05-03 | 2028-05-28 | 2028-07-29 | Not Available | 2028-07-30 | 2028-08-21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRNU | kh.br.as.idn.15 | Bali | 9142.3823 | FD | 434 | 1236 | 1542 | 1109 | 2028-04-27 | 2028-04-12 | 2028-04-22 | 2028-04-28 | 2028-05-12 | 2028-05-13 | 2028-06-07 | 2028-08-04 | Not Available | 2028-08-06 | 2028-08-28 | 2028-04-27 | 2028-04-12 | 2028-04-22 | 2028-04-28 | 2028-05-12 | 2028-05-13 | 2028-06-07 | 2028-08-04 | Not Available | 2028-08-06 | 2028-08-28 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRML | kh.br.as.idn.18 | North Maluku | 3589.092 | FD | 58 | 164 | 205 | 150 | 2028-04-28 | 2028-04-13 | 2028-04-23 | 2028-04-29 | 2028-05-13 | 2028-05-14 | 2028-06-08 | 2028-08-05 | Not Available | 2028-08-07 | 2028-08-29 | 2028-04-28 | 2028-04-13 | 2028-04-23 | 2028-04-29 | 2028-05-13 | 2028-05-14 | 2028-06-08 | 2028-08-05 | Not Available | 2028-08-07 | 2028-08-29 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRML | kh.br.as.idn.17 | Maluku | 4499.7502 | FD | 83 | 237 | 295 | 212 | 2028-04-29 | 2028-04-14 | 2028-04-24 | 2028-04-30 | 2028-05-14 | 2028-05-15 | 2028-06-09 | 2028-08-06 | Not Available | 2028-08-08 | 2028-08-30 | 2028-04-29 | 2028-04-14 | 2028-04-24 | 2028-04-30 | 2028-05-14 | 2028-05-15 | 2028-06-09 | 2028-08-06 | Not Available | 2028-08-08 | 2028-08-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRPP | kh.br.as.idn.20 | Papua East | 6725.8425 | FD | 131 | 374 | 467 | 335 | 2028-05-01 | 2028-04-16 | 2028-04-26 | 2028-05-02 | 2028-05-16 | 2028-05-17 | 2028-06-11 | 2028-08-08 | Not Available | 2028-08-10 | 2028-09-01 | 2028-05-01 | 2028-04-16 | 2028-04-26 | 2028-05-02 | 2028-05-16 | 2028-05-17 | 2028-06-11 | 2028-08-08 | Not Available | 2028-08-10 | 2028-09-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indonesia | IDDRPP | kh.br.as.idn.19 | Papua West | 6988.9587 | FD | 114 | 324 | 404 | 291 | 2028-05-03 | 2028-04-18 | 2028-04-28 | 2028-05-04 | 2028-05-18 | 2028-05-19 | 2028-06-13 | 2028-08-10 | Not Available | 2028-08-12 | 2028-09-02 | 2028-05-03 | 2028-04-18 | 2028-04-28 | 2028-05-04 | 2028-05-18 | 2028-05-19 | 2028-06-13 | 2028-08-10 | Not Available | 2028-08-12 | 2028-09-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR2 | kh.br.as.phl.08 | Mimaropa | 8940.6126 | FD | 94 | 179 | 194 | 756 | 2028-03-26 | 2028-03-11 | 2028-03-21 | 2028-03-27 | 2028-04-04 | 2028-04-05 | 2028-04-30 | 2028-07-13 | Not Available | 2028-07-14 | 2028-08-05 | 2028-03-26 | 2028-03-11 | 2028-03-21 | 2028-03-27 | 2028-04-04 | 2028-04-05 | 2028-04-30 | 2028-07-13 | Not Available | 2028-07-14 | 2028-08-05 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR2 | kh.br.as.phl.09 | Western Visayas | 7945.4468 | FD | 137 | 262 | 282 | 1107 | 2028-05-07 | 2028-04-22 | 2028-05-02 | 2028-05-08 | 2028-05-16 | 2028-05-17 | 2028-06-11 | 2028-08-14 | Not Available | 2028-08-16 | 2028-09-07 | 2028-05-07 | 2028-04-22 | 2028-05-02 | 2028-05-08 | 2028-05-16 | 2028-05-17 | 2028-06-11 | 2028-08-14 | Not Available | 2028-08-16 | 2028-09-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR2 | kh.br.as.phl.18 | Negros Island | 9294.4172 | FD | 138 | 264 | 285 | 1115 | 2028-05-12 | 2028-04-27 | 2028-05-07 | 2028-05-13 | 2028-05-21 | 2028-05-22 | 2028-06-16 | 2028-08-20 | Not Available | 2028-08-21 | 2028-09-10 | 2028-05-12 | 2028-04-27 | 2028-05-07 | 2028-05-13 | 2028-05-21 | 2028-05-22 | 2028-06-16 | 2028-08-20 | Not Available | 2028-08-21 | 2028-09-10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR2 | kh.br.as.phl.11 | Eastern Visayas | 6975.1976 | FD | 132 | 252 | 271 | 1064 | 2028-05-15 | 2028-04-30 | 2028-05-10 | 2028-05-16 | 2028-05-24 | 2028-05-25 | 2028-06-19 | 2028-08-23 | Not Available | 2028-08-25 | 2028-09-15 | 2028-05-15 | 2028-04-30 | 2028-05-10 | 2028-05-16 | 2028-05-24 | 2028-05-25 | 2028-06-19 | 2028-08-23 | Not Available | 2028-08-25 | 2028-09-15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR2 | kh.br.as.phl.10 | Central Visayas | 8945.6474 | FD | 190 | 363 | 391 | 1533 | 2028-05-24 | 2028-05-09 | 2028-05-19 | 2028-05-25 | 2028-06-03 | 2028-06-04 | 2028-06-28 | 2028-09-03 | Not Available | 2028-09-04 | 2028-09-26 | 2028-05-24 | 2028-05-09 | 2028-05-19 | 2028-05-25 | 2028-06-03 | 2028-06-04 | 2028-06-28 | 2028-09-03 | Not Available | 2028-09-04 | 2028-09-26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.06 | Manila | 4315.9357 | FD | 587 | 1122 | 1206 | 4737 | 2028-06-04 | 2028-05-20 | 2028-05-30 | 2028-06-05 | 2028-06-13 | 2028-06-14 | 2028-07-09 | 2028-09-11 | Not Available | 2028-09-13 | 2028-10-05 | 2028-06-04 | 2028-05-20 | 2028-05-30 | 2028-06-05 | 2028-06-13 | 2028-06-14 | 2028-07-09 | 2028-09-11 | Not Available | 2028-09-13 | 2028-10-05 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.07 | Bicol | 6904.7119 | FD | 176 | 337 | 362 | 1424 | 2028-06-09 | 2028-05-25 | 2028-06-04 | 2028-06-10 | 2028-06-18 | 2028-06-19 | 2028-07-14 | 2028-09-13 | Not Available | 2028-09-15 | 2028-10-07 | 2028-06-09 | 2028-05-25 | 2028-06-04 | 2028-06-10 | 2028-06-18 | 2028-06-19 | 2028-07-14 | 2028-09-13 | Not Available | 2028-09-15 | 2028-10-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.04 | Central Luzon | 15235.0521 | FD | 540 | 1033 | 1110 | 4364 | 2028-06-22 | 2028-06-07 | 2028-06-17 | 2028-06-23 | 2028-07-01 | 2028-07-02 | 2028-07-27 | 2028-09-28 | Not Available | 2028-09-30 | 2028-10-22 | 2028-06-22 | 2028-06-07 | 2028-06-17 | 2028-06-23 | 2028-07-01 | 2028-07-02 | 2028-07-27 | 2028-09-28 | Not Available | 2028-09-30 | 2028-10-22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.05 | Calabarzon | 14445.8084 | FD | 704 | 1347 | 1449 | 5688 | 2028-07-10 | 2028-06-25 | 2028-07-05 | 2028-07-11 | 2028-07-19 | 2028-07-20 | 2028-08-14 | 2028-10-14 | Not Available | 2028-10-15 | 2028-11-06 | 2028-07-10 | 2028-06-25 | 2028-07-05 | 2028-07-11 | 2028-07-19 | 2028-07-20 | 2028-08-14 | 2028-10-14 | Not Available | 2028-10-15 | 2028-11-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.02 | Cordillera | 4142.3365 | FD | 52 | 100 | 107 | 420 | 2028-07-11 | 2028-06-26 | 2028-07-06 | 2028-07-12 | 2028-07-20 | 2028-07-21 | 2028-08-16 | 2028-10-15 | Not Available | 2028-10-16 | 2028-11-07 | 2028-07-11 | 2028-06-26 | 2028-07-06 | 2028-07-12 | 2028-07-20 | 2028-07-21 | 2028-08-16 | 2028-10-15 | Not Available | 2028-10-16 | 2028-11-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.03 | Cagayan Valley | 8833.822 | FD | 107 | 205 | 221 | 864 | 2028-07-14 | 2028-06-29 | 2028-07-09 | 2028-07-15 | 2028-07-23 | 2028-07-24 | 2028-08-18 | 2028-10-19 | Not Available | 2028-10-20 | 2028-11-11 | 2028-07-14 | 2028-06-29 | 2028-07-09 | 2028-07-15 | 2028-07-23 | 2028-07-24 | 2028-08-18 | 2028-10-19 | Not Available | 2028-10-20 | 2028-11-11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR1 | kh.br.as.phl.01 | Ilocos | 7974.7425 | FD | 154 | 294 | 317 | 1242 | 2028-07-20 | 2028-07-05 | 2028-07-15 | 2028-07-21 | 2028-07-29 | 2028-07-30 | 2028-08-24 | 2028-10-23 | Not Available | 2028-10-24 | 2028-11-15 | 2028-07-20 | 2028-07-05 | 2028-07-15 | 2028-07-21 | 2028-07-29 | 2028-07-30 | 2028-08-24 | 2028-10-23 | Not Available | 2028-10-24 | 2028-11-15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.17 | Bangsamoro | 3307.8803 | FD | 143 | 275 | 294 | 1157 | 2028-07-22 | 2028-07-07 | 2028-07-17 | 2028-07-23 | 2028-07-31 | 2028-08-01 | 2028-08-26 | 2028-10-24 | Not Available | 2028-10-25 | 2028-11-16 | 2028-07-22 | 2028-07-07 | 2028-07-17 | 2028-07-23 | 2028-07-31 | 2028-08-01 | 2028-08-26 | 2028-10-24 | Not Available | 2028-10-25 | 2028-11-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.15 | Soccskargen | 10514.3085 | FD | 127 | 242 | 262 | 1021 | 2028-07-28 | 2028-07-13 | 2028-07-23 | 2028-07-29 | 2028-08-06 | 2028-08-07 | 2028-09-01 | 2028-10-30 | Not Available | 2028-10-31 | 2028-11-22 | 2028-07-28 | 2028-07-13 | 2028-07-23 | 2028-07-29 | 2028-08-06 | 2028-08-07 | 2028-09-01 | 2028-10-30 | Not Available | 2028-10-31 | 2028-11-22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.16 | Caraga | 4840.8377 | FD | 81 | 156 | 168 | 659 | 2028-07-30 | 2028-07-15 | 2028-07-25 | 2028-07-31 | 2028-08-08 | 2028-08-09 | 2028-09-03 | 2028-11-02 | Not Available | 2028-11-03 | 2028-11-25 | 2028-07-30 | 2028-07-15 | 2028-07-25 | 2028-07-31 | 2028-08-08 | 2028-08-09 | 2028-09-03 | 2028-11-02 | Not Available | 2028-11-03 | 2028-11-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.13 | Northern Mindanao | 10575.0029 | FD | 146 | 279 | 300 | 1176 | 2028-08-05 | 2028-07-21 | 2028-07-31 | 2028-08-06 | 2028-08-14 | 2028-08-16 | 2028-09-09 | 2028-11-07 | Not Available | 2028-11-08 | 2028-11-30 | 2028-08-05 | 2028-07-21 | 2028-07-31 | 2028-08-06 | 2028-08-14 | 2028-08-16 | 2028-09-09 | 2028-11-07 | Not Available | 2028-11-08 | 2028-11-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.14 | Davao | 11205.2023 | FD | 152 | 291 | 313 | 1227 | 2028-08-11 | 2028-07-27 | 2028-08-06 | 2028-08-12 | 2028-08-21 | 2028-08-22 | 2028-09-16 | 2028-11-13 | Not Available | 2028-11-14 | 2028-12-06 | 2028-08-11 | 2028-07-27 | 2028-08-06 | 2028-08-12 | 2028-08-21 | 2028-08-22 | 2028-09-16 | 2028-11-13 | Not Available | 2028-11-14 | 2028-12-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philippines | PHDR3 | kh.br.as.phl.12 | Zamboanga Peninsula | 5603.0375 | FD | 112 | 215 | 231 | 906 | 2028-08-13 | 2028-07-29 | 2028-08-08 | 2028-08-14 | 2028-08-22 | 2028-08-23 | 2028-09-17 | 2028-11-16 | Not Available | 2028-11-17 | 2028-12-07 | 2028-08-13 | 2028-07-29 | 2028-08-08 | 2028-08-14 | 2028-08-22 | 2028-08-23 | 2028-09-17 | 2028-11-16 | Not Available | 2028-11-17 | 2028-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Planner Sequence
Market | Deployment Region | BR Name | BR ID | Planner BR Sequence | Deployment Region | Planner DR Sequence
Brazil | BRDRSP | São Paulo | kh.br.sa.bra.08_A | 1 | BRDRSP | 1
Brazil | BRDRSP | Campinas | kh.br.sa.bra.08_C | 2 | BRDRRIO | 2
Brazil | BRDRSP | Ribeirão Preto | kh.br.sa.bra.08_D | 3 | BRDRNE | 3
Brazil | BRDRSP | São José dos Campos | kh.br.sa.bra.08_B | 4 | BRDRN | 4
Brazil | BRDRRIO | Rio de Janeiro | kh.br.sa.bra.11_A | 5 | BRDRC_A | 5
Brazil | BRDRRIO | Campos dos Goytacazes | kh.br.sa.bra.11_B | 6 | BRDRS_A | 6
Brazil | BRDRRIO | Vitória | kh.br.sa.bra.11_C | 7 | BRDRW | 7
Brazil | BRDRNE | Salvador | kh.br.sa.bra.16 | 8
Brazil | BRDRNE | Recife | kh.br.sa.bra.17 | 9
Brazil | BRDRNE | Natal | kh.br.sa.bra.18 | 10
Brazil | BRDRN | Sao Luis | kh.br.sa.bra.13 | 11
Brazil | BRDRN | Teresina | kh.br.sa.bra.14 | 12
Brazil | BRDRN | Fortaleza | kh.br.sa.bra.15 | 13
Brazil | BRDRN | Palmas | kh.br.sa.bra.12 | 14
Brazil | BRDRC_A | Uberlândia | kh.br.sa.bra.10_B | 15
Brazil | BRDRC_A | Belo Horizonte | kh.br.sa.bra.10_A | 16
Brazil | BRDRC_A | Goiânia | kh.br.sa.bra.09_B | 17
Brazil | BRDRC_A | Brasília | kh.br.sa.bra.09_A | 18
Brazil | BRDRS_A | Curitiba | kh.br.sa.bra.07_A | 19
Brazil | BRDRS_A | Porto Alegre | kh.br.sa.bra.06 | 20
Brazil | BRDRS_A | Corumba | kh.br.sa.bra.05 | 21
Brazil | BRDRS_A | Joinville | kh.br.sa.bra.07_B | 22
Brazil | BRDRW | Cuiaba | kh.br.sa.bra.04 | 23
Brazil | BRDRW | Porto Velho | kh.br.sa.bra.01 | 24
Brazil | BRDRW | Belem | kh.br.sa.bra.03 | 25
Brazil | BRDRW | Manaus | kh.br.sa.bra.02 | 26

## Country End date
Country | Status | Country End Dates & Variance | [10 empty] | Addressing Start & End date
|  | Naming |  |  | DC2 |  |  | Addressing |  |  | Country | Status | LTP 9/21 | [11 empty] | Country | Status | LTP 9/14 | [5 empty] | Country | Status | MPRA End Dates |  |  | Remarks | Markets | Addressing Initiation Date
|  | LTP 9/21 | LTP 9/14 | Naming QA Variance | LTP 9/21 | LTP 9/14 | DC2 Variance | LTP 9/21 | LTP 9/14 | MPRA Stage End date Variance |  |  | Naming QA | Naming QA Variance | HLA Stage Start date | HLA Stage Start date Variance | HLA Stage End date | HLA Stage End date Variance | ADC Stage End date | ADC Stage End date Variance | DC2 | DC2 Variance | MPRA Stage End date | MPRA Stage End date Variance |  |  | Naming QA | HLA Phase start date | HLA Phase end date | ADC Phase end date | DC2 | MPRA Phase end date |  |  | LTP 9/21 | LTP 9/14 | Variance
Brazil_P2 | WIP | 2026-11-24 | 2026-11-24 | 0 | 2027-02-19 | 2027-02-19 | 0 | 2027-06-08 | 2027-06-08 | 0 | Brazil_P2 | WIP | 2026-11-24 | 0 | 2026-01-06 | 0 | 2026-12-16 | 0 | 2027-01-16 | 0 | 2027-02-19 | 0 | 2027-06-08 | 0 | Brazil_P2 | WIP | 2026-11-24 | 2026-01-06 | 2026-12-16 | 2027-01-16 | 2027-02-19 | 2027-06-08 | Brazil_P2 | WIP | 2027-06-08 | 2027-06-08 | 0 | - | Brazil_P2 | 2026-01-06
Indonesia | YTS | 2028-05-03 | 2028-05-03 | 0 | 2028-08-10 | 2028-08-10 | 0 | 2028-09-02 | 2028-09-02 | 0 | Indonesia | YTS | 2028-05-03 | 0 | 2027-07-27 | 0 | 2028-05-18 | 0 | 2028-06-13 | 0 | 2028-08-10 | 0 | 2028-09-02 | 0 | Indonesia | YTS | 2028-05-03 | 2027-07-27 | 2028-05-18 | 2028-06-13 | 2028-08-10 | 2028-09-02 | Indonesia | YTS | 2028-09-02 | 2028-09-02 | 0 | - | Indonesia | 2027-07-27
Philippines | YTS | 2028-08-13 | 2028-08-13 | 0 | 2028-11-16 | 2028-11-16 | 0 | 2028-12-07 | 2028-12-07 | 0 | Philippines | YTS | 2028-08-13 | 0 | 2028-03-27 | 0 | 2028-08-22 | 0 | 2028-09-17 | 0 | 2028-11-16 | 0 | 2028-12-07 | 0 | Philippines | YTS | 2028-08-13 | 2028-03-27 | 2028-08-22 | 2028-09-17 | 2028-11-16 | 2028-12-07 | Philippines | YTS | 2028-12-07 | 2028-12-07 | 0 | - | Philippines | 2028-03-27
Formulas:
Country End Dates & Variance = [Addressing Start & End date]
MPRA End Dates = [Addressing]

## Variance in LTP vs LTP
[6 empty] | Naming QA Acceptance |  |  | DC2 |  |  | Addressing Submission |  |  |  | Only Ranges1 & Ranges2 worked in ADC Stage | Full Drive BRs | Completed
Country | DR | Build Region ID | Build Region Name | Phase | KMS | LTP 9/14 | LTP 9/21 | Variance | LTP 9/14 | LTP 9/21 | Variance | LTP 9/14 | LTP 9/21 | Variance | Remarks | Ranges1, Ranges2 & Access Points worked in ADC Stage | Planned/Yet to start | In Progress
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_A | São Paulo | Phase2 | 34714 | 2025-12-31 | 2025-12-31 | 0 | 2026-06-20 | 2026-06-20 | 0 | 2026-09-23 | 2026-09-23 | 0 | -
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_C | Campinas | Phase2 | 23453 | 2026-01-07 | 2026-01-07 | 0 | 2026-08-09 | 2026-08-09 | 0 | 2026-10-25 | 2026-10-25 | 0 | -
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_D | Ribeirão Preto | Phase2 | 23151 | 2026-01-19 | 2026-01-19 | 0 | 2026-09-06 | 2026-09-06 | 0 | 2026-11-22 | 2026-11-22 | 0 | -
Brazil_P2 | BRDRSP_P2 | kh.br.sa.bra.08_B | São José dos Campos | Phase2 | 26018 | 2026-01-27 | 2026-01-27 | 0 | 2026-09-18 | 2026-09-18 | 0 | 2026-11-27 | 2026-11-27 | 0 | -
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_A | Rio de Janeiro | Phase2 | 14299 | 2026-01-29 | 2026-01-29 | 0 | 2026-07-07 | 2026-07-07 | 0 | 2026-09-28 | 2026-09-28 | 0 | -
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_B | Campos dos Goytacazes | Phase2 | 18163 | 2026-01-31 | 2026-01-31 | 0 | 2026-07-12 | 2026-07-12 | 0 | 2026-10-12 | 2026-10-12 | 0 | -
Brazil_P2 | BRDRRIO_P2 | kh.br.sa.bra.11_C | Vitória | Phase2 | 7469 | 2026-02-06 | 2026-02-06 | 0 | 2026-07-21 | 2026-07-21 | 0 | 2026-10-06 | 2026-10-06 | 0 | -
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.16 | Salvador | Phase2 | 23933 | 2026-02-22 | 2026-02-22 | 0 | 2026-10-04 | 2026-10-04 | 0 | 2026-12-13 | 2026-12-13 | 0 | -
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.17 | Recife | Phase2 | 22668 | 2026-03-10 | 2026-03-10 | 0 | 2026-10-12 | 2026-10-12 | 0 | 2026-12-22 | 2026-12-22 | 0 | -
Brazil_P2 | BRDRNE_P2 | kh.br.sa.bra.18 | Natal | Phase2 | 14335 | 2026-04-02 | 2026-04-02 | 0 | 2026-10-21 | 2026-10-21 | 0 | 2026-12-28 | 2026-12-28 | 0 | -
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.13 | Sao Luis | Phase2 | 11777 | 2026-03-23 | 2026-03-23 | 0 | 2026-10-25 | 2026-10-25 | 0 | 2027-01-02 | 2027-01-02 | 0 | -
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.14 | Teresina | Phase2 | 8173 | 2026-03-24 | 2026-03-24 | 0 | 2026-10-28 | 2026-10-28 | 0 | 2027-01-05 | 2027-01-05 | 0 | -
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.15 | Fortaleza | Phase2 | 15472 | 2026-04-23 | 2026-04-23 | 0 | 2026-11-07 | 2026-11-07 | 0 | 2027-01-13 | 2027-01-13 | 0 | -
Brazil_P2 | BRDRN_P2 | kh.br.sa.bra.12 | Palmas | Phase2 | 6544 | 2026-05-06 | 2026-05-06 | 0 | 2026-11-12 | 2026-11-12 | 0 | 2027-01-21 | 2027-01-21 | 0 | -
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.10_B | Uberlândia | Phase2 | 24034 | 2026-03-17 | 2026-03-17 | 0 | 2026-11-28 | 2026-11-28 | 0 | 2027-02-28 | 2027-02-28 | 0 | -
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.10_A | Belo Horizonte | Phase2 | 18327 | 2026-05-13 | 2026-05-13 | 0 | 2026-12-13 | 2026-12-13 | 0 | 2027-03-25 | 2027-03-25 | 0 | -
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.09_B | Goiânia | Phase2 | 27365 | 2026-06-28 | 2026-06-28 | 0 | 2026-12-27 | 2026-12-27 | 0 | 2027-04-07 | 2027-04-07 | 0 | -
Brazil_P2 | BRDRC_A_P2 | kh.br.sa.bra.09_A | Brasília | Phase2 | 8952 | 2026-07-09 | 2026-07-09 | 0 | 2027-01-02 | 2027-01-02 | 0 | 2027-04-17 | 2027-04-17 | 0 | -
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.07_A | Curitiba | Phase2 | 28875 | 2026-10-17 | 2026-10-17 | 0 | 2027-01-17 | 2027-01-17 | 0 | 2027-05-03 | 2027-05-03 | 0 | -
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.06 | Porto Alegre | Phase2 | 24358 | 2026-07-30 | 2026-07-30 | 0 | 2027-01-27 | 2027-01-27 | 0 | 2027-05-12 | 2027-05-12 | 0 | -
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.05 | Corumba | Phase2 | 12741 | 2026-08-11 | 2026-08-11 | 0 | 2027-02-01 | 2027-02-01 | 0 | 2027-05-17 | 2027-05-17 | 0 | -
Brazil_P2 | BRDRS_A_P2 | kh.br.sa.bra.07_B | Joinville | Phase2 | 16540 | 2026-11-24 | 2026-11-24 | 0 | 2027-02-09 | 2027-02-09 | 0 | 2027-05-25 | 2027-05-25 | 0 | -
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.04 | Cuiaba | Phase2 | 13464 | 2026-08-19 | 2026-08-19 | 0 | 2027-02-16 | 2027-02-16 | 0 | 2027-05-31 | 2027-05-31 | 0 | -
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.01 | Porto Velho | Phase2 | 5848 | 2026-08-25 | 2026-08-25 | 0 | 2027-02-17 | 2027-02-17 | 0 | 2027-06-04 | 2027-06-04 | 0 | -
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.03 | Belem | Phase2 | 8948 | 2026-09-07 | 2026-09-07 | 0 | 2027-02-19 | 2027-02-19 | 0 | 2027-06-06 | 2027-06-06 | 0 | -
Brazil_P2 | BRDRW_P2 | kh.br.sa.bra.02 | Manaus | Phase2 | 13424 | 2026-09-11 | 2026-09-11 | 0 | 2027-02-19 | 2027-02-19 | 0 | 2027-06-08 | 2027-06-08 | 0 | Tentative Brazil Phase2 completion time (8-Jun-27)
Indonesia | IDDRSM | kh.br.as.idn.01 | Aceh | FD | 7632.6119 | 2027-07-26 | 2027-07-26 | 0 | 2027-11-28 | 2027-11-28 | 0 | 2027-12-14 | 2027-12-14 | 0 | -
Indonesia | IDDRSM | kh.br.as.idn.05 | Lampung | FD | 11419.8559 | 2027-08-28 | 2027-08-28 | 0 | 2027-12-18 | 2027-12-18 | 0 | 2028-01-10 | 2028-01-10 | 0 | -
Indonesia | IDDRSM | kh.br.as.idn.04 | Sumatra Island South | FD | 21126.6364 | 2027-09-09 | 2027-09-09 | 0 | 2028-01-02 | 2028-01-02 | 0 | 2028-01-25 | 2028-01-25 | 0 | -
Indonesia | IDDRSM | kh.br.as.idn.03 | Sumatra Island Central | FD | 20891.2863 | 2027-09-21 | 2027-09-21 | 0 | 2028-01-14 | 2028-01-14 | 0 | 2028-02-07 | 2028-02-07 | 0 | -
Indonesia | IDDRSM | kh.br.as.idn.02 | Medan | FD | 17053.2041 | 2027-09-29 | 2027-09-29 | 0 | 2028-01-28 | 2028-01-28 | 0 | 2028-02-20 | 2028-02-20 | 0 | -
Indonesia | IDDRKA | kh.br.as.idn.07 | West Kalimantan | FD | 24285.3839 | 2027-10-03 | 2027-10-03 | 0 | 2028-02-11 | 2028-02-11 | 0 | 2028-03-05 | 2028-03-05 | 0 | -
Indonesia | IDDRKA | kh.br.as.idn.06 | East Kalimantan | FD | 19072.7125 | 2027-10-06 | 2027-10-06 | 0 | 2028-02-22 | 2028-02-22 | 0 | 2028-03-16 | 2028-03-16 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.09 | Jakarta | FD | 3670.6587 | 2027-10-14 | 2027-10-14 | 0 | 2028-03-03 | 2028-03-03 | 0 | 2028-03-26 | 2028-03-26 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.08 | Banten | FD | 7393.3955 | 2027-10-24 | 2027-10-24 | 0 | 2028-03-23 | 2028-03-23 | 0 | 2028-04-15 | 2028-04-15 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.10_A | West Java A | FD | 11005.7701 | 2027-11-12 | 2027-11-12 | 0 | 2028-04-08 | 2028-04-08 | 0 | 2028-05-01 | 2028-05-01 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.12_C | East Java C | FD | 13706.3789 | 2027-11-29 | 2027-11-29 | 0 | 2028-04-24 | 2028-04-24 | 0 | 2028-05-17 | 2028-05-17 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.11_C | Yogyakarta | FD | 13092.8417 | 2027-12-17 | 2027-12-17 | 0 | 2028-05-07 | 2028-05-07 | 0 | 2028-05-30 | 2028-05-30 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.12_B | East Java B | FD | 11238.8128 | 2028-01-07 | 2028-01-07 | 0 | 2028-05-18 | 2028-05-18 | 0 | 2028-06-10 | 2028-06-10 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.11_B | Central Java B | FD | 9545.187 | 2028-01-23 | 2028-01-23 | 0 | 2028-05-28 | 2028-05-28 | 0 | 2028-06-20 | 2028-06-20 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.12_A | East Java A | FD | 11006.766 | 2028-02-08 | 2028-02-08 | 0 | 2028-06-10 | 2028-06-10 | 0 | 2028-07-03 | 2028-07-03 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.10_C | West Java C | FD | 9856.5905 | 2028-02-22 | 2028-02-22 | 0 | 2028-06-20 | 2028-06-20 | 0 | 2028-07-13 | 2028-07-13 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.10_B | West Java B | FD | 9493.5621 | 2028-03-08 | 2028-03-08 | 0 | 2028-06-30 | 2028-06-30 | 0 | 2028-07-23 | 2028-07-23 | 0 | -
Indonesia | IDDRJW | kh.br.as.idn.11_A | Central Java A | FD | 8464.8366 | 2028-03-23 | 2028-03-23 | 0 | 2028-07-09 | 2028-07-09 | 0 | 2028-08-01 | 2028-08-01 | 0 | -
Indonesia | IDDRSL | kh.br.as.idn.14 | Celebes South | FD | 19403.9646 | 2028-04-07 | 2028-04-07 | 0 | 2028-07-21 | 2028-07-21 | 0 | 2028-08-12 | 2028-08-12 | 0 | -
Indonesia | IDDRSL | kh.br.as.idn.13 | Celebes North | FD | 9176.757 | 2028-04-11 | 2028-04-11 | 0 | 2028-07-24 | 2028-07-24 | 0 | 2028-08-16 | 2028-08-16 | 0 | -
Indonesia | IDDRNU | kh.br.as.idn.16 | East Nusa Tenggara | FD | 10516.7618 | 2028-04-17 | 2028-04-17 | 0 | 2028-07-29 | 2028-07-29 | 0 | 2028-08-21 | 2028-08-21 | 0 | -
Indonesia | IDDRNU | kh.br.as.idn.15 | Bali | FD | 9142.3823 | 2028-04-27 | 2028-04-27 | 0 | 2028-08-04 | 2028-08-04 | 0 | 2028-08-28 | 2028-08-28 | 0 | -
Indonesia | IDDRML | kh.br.as.idn.18 | North Maluku | FD | 3589.092 | 2028-04-28 | 2028-04-28 | 0 | 2028-08-05 | 2028-08-05 | 0 | 2028-08-29 | 2028-08-29 | 0 | -
Indonesia | IDDRML | kh.br.as.idn.17 | Maluku | FD | 4499.7502 | 2028-04-29 | 2028-04-29 | 0 | 2028-08-06 | 2028-08-06 | 0 | 2028-08-30 | 2028-08-30 | 0 | -
Indonesia | IDDRPP | kh.br.as.idn.20 | Papua East | FD | 6725.8425 | 2028-05-01 | 2028-05-01 | 0 | 2028-08-08 | 2028-08-08 | 0 | 2028-09-01 | 2028-09-01 | 0 | -
Indonesia | IDDRPP | kh.br.as.idn.19 | Papua West | FD | 6988.9587 | 2028-05-03 | 2028-05-03 | 0 | 2028-08-10 | 2028-08-10 | 0 | 2028-09-02 | 2028-09-02 | 0 | Tentative Indonesia completion time (2-Sep-28)
Philippines | PHDR2 | kh.br.as.phl.08 | Mimaropa | FD | 8940.6126 | 2028-03-26 | 2028-03-26 | 0 | 2028-07-13 | 2028-07-13 | 0 | 2028-08-05 | 2028-08-05 | 0 | -
Philippines | PHDR2 | kh.br.as.phl.09 | Western Visayas | FD | 7945.4468 | 2028-05-07 | 2028-05-07 | 0 | 2028-08-14 | 2028-08-14 | 0 | 2028-09-07 | 2028-09-07 | 0 | -
Philippines | PHDR2 | kh.br.as.phl.18 | Negros Island | FD | 9294.4172 | 2028-05-12 | 2028-05-12 | 0 | 2028-08-20 | 2028-08-20 | 0 | 2028-09-10 | 2028-09-10 | 0 | -
Philippines | PHDR2 | kh.br.as.phl.11 | Eastern Visayas | FD | 6975.1976 | 2028-05-15 | 2028-05-15 | 0 | 2028-08-23 | 2028-08-23 | 0 | 2028-09-15 | 2028-09-15 | 0 | -
Philippines | PHDR2 | kh.br.as.phl.10 | Central Visayas | FD | 8945.6474 | 2028-05-24 | 2028-05-24 | 0 | 2028-09-03 | 2028-09-03 | 0 | 2028-09-26 | 2028-09-26 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.06 | Manila | FD | 4315.9357 | 2028-06-04 | 2028-06-04 | 0 | 2028-09-11 | 2028-09-11 | 0 | 2028-10-05 | 2028-10-05 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.07 | Bicol | FD | 6904.7119 | 2028-06-09 | 2028-06-09 | 0 | 2028-09-13 | 2028-09-13 | 0 | 2028-10-07 | 2028-10-07 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.04 | Central Luzon | FD | 15235.0521 | 2028-06-22 | 2028-06-22 | 0 | 2028-09-28 | 2028-09-28 | 0 | 2028-10-22 | 2028-10-22 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.05 | Calabarzon | FD | 14445.8084 | 2028-07-10 | 2028-07-10 | 0 | 2028-10-14 | 2028-10-14 | 0 | 2028-11-06 | 2028-11-06 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.02 | Cordillera | FD | 4142.3365 | 2028-07-11 | 2028-07-11 | 0 | 2028-10-15 | 2028-10-15 | 0 | 2028-11-07 | 2028-11-07 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.03 | Cagayan Valley | FD | 8833.822 | 2028-07-14 | 2028-07-14 | 0 | 2028-10-19 | 2028-10-19 | 0 | 2028-11-11 | 2028-11-11 | 0 | -
Philippines | PHDR1 | kh.br.as.phl.01 | Ilocos | FD | 7974.7425 | 2028-07-20 | 2028-07-20 | 0 | 2028-10-23 | 2028-10-23 | 0 | 2028-11-15 | 2028-11-15 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.17 | Bangsamoro | FD | 3307.8803 | 2028-07-22 | 2028-07-22 | 0 | 2028-10-24 | 2028-10-24 | 0 | 2028-11-16 | 2028-11-16 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.15 | Soccskargen | FD | 10514.3085 | 2028-07-28 | 2028-07-28 | 0 | 2028-10-30 | 2028-10-30 | 0 | 2028-11-22 | 2028-11-22 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.16 | Caraga | FD | 4840.8377 | 2028-07-30 | 2028-07-30 | 0 | 2028-11-02 | 2028-11-02 | 0 | 2028-11-25 | 2028-11-25 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.13 | Northern Mindanao | FD | 10575.0029 | 2028-08-05 | 2028-08-05 | 0 | 2028-11-07 | 2028-11-07 | 0 | 2028-11-30 | 2028-11-30 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.14 | Davao | FD | 11205.2023 | 2028-08-11 | 2028-08-11 | 0 | 2028-11-13 | 2028-11-13 | 0 | 2028-12-06 | 2028-12-06 | 0 | -
Philippines | PHDR3 | kh.br.as.phl.12 | Zamboanga Peninsula | FD | 5603.0375 | 2028-08-13 | 2028-08-13 | 0 | 2028-11-16 | 2028-11-16 | 0 | 2028-12-07 | 2028-12-07 | 0 | Tentative Philippines completion time (7-Dec-28)

## Demand vs Supply
LTP 21-Sep-2026 :: Demand Vs Supply
Month | Working days | Total HC | Daily Login HC | Shrinkage | Attrition | Total Available Capacity | Inventory from Upstream (Naming QA) | Inventory from Upstream (DC2) | Inventory from Product Improvement | Net Inventory coming in current month | Unused Inventory | Remarks
Sep'26 | 8 | 96 | 69 | 90% | 98.5% | 691.2 | 1967.2 | 7263.4667 | 0 | 9230.6667 | 8539.4667 | 20 HC movement extended for Additional Finishing Task & 40 HC for moved temporarily 25 HC moved (Jul'26 to Sep'26) to QA temporarily 40 HC for Highway Service Road task
Oct'26 | 20 | 217.685 | 155 | 90% | 98.5% | 3918.33 | 1271.0667 | 3627.7333 | 0 | 4898.8 | 9519.9367 | 20+40 HC move back from Additional Finishing Task 25 HC move back from QA 40 HC move back from Highway Service Road task
Nov'26 | 20 | 214.4197 | 153 | 90% | 98.5% | 3859.5551 | 978 | 3444.6667 | 0 | 4422.6667 | 10083.0483 | -
Dec'26 | 22 | 211.2034 | 151 | 90% | 98.5% | 4181.8279 | 0 | 2709.2 | 0 | 2709.2 | 8610.4204 | -
Jan'27 | 18 | 208.0354 | 149 | 90% | 98.5% | 3370.1731 | 0 | 4431.8667 | 0 | 4431.8667 | 9672.1139 | -
Feb'27 | 20 | 204.9148 | 146 | 90% | 98.5% | 3688.4672 | 0 | 4189.2 | 0 | 4189.2 | 10172.8467 | -
Mar'27 | 22 | 201.8411 | 144 | 90% | 98.5% | 3996.4543 | 0 | 0 | 0 | 0 | 6176.3924 | -
Apr'27 | 19 | 183.8135 | 131 | 90% | 98.5% | 3143.211 | 0 | 0 | 0 | 0 | 3033.1814 | FunT HC (15) moved to complete IDN FunT
May'27 | 22 | 196.0563 | 140 | 90% | 98.5% | 3881.9148 | 0 | 0 | 0 | 0 | -848.7334 | FunT HC (15) moved back to Production
Jun'27 | 21 | 193.1155 | 138 | 90% | 98.5% | 3649.8822 | 0 | 0 | 0 | 0 | -3649.8822 | Tentative Brazil Phase2 completion time (8-Jun-27)
Jul'27 | 22 | 190.2187 | 136 | 90% | 98.5% | 3766.3308 | 202.5333 | 0 | 31.6 | 234.1333 | -3532.1975 | -
Aug'27 | 22 | 187.3654 | 134 | 90% | 98.5% | 3709.8359 | 346.1333 | 0 | 54 | 400.1333 | -3309.7025 | -
Sep'27 | 21 | 184.555 | 132 | 90% | 98.5% | 3488.0889 | 1701.3333 | 0 | 265.7333 | 1967.0667 | -1521.0222 | -
Oct'27 | 20 | 181.7866 | 130 | 90% | 98.5% | 3272.1595 | 1502 | 0 | 234.5333 | 1736.5333 | -1535.6262 | -
Nov'27 | 21 | 179.0598 | 128 | 90% | 98.5% | 3384.231 | 1202.1333 | 81.0667 | 187.8667 | 1471.0667 | -1913.1643 | -
Dec'27 | 23 | 161.3739 | 115 | 90% | 98.5% | 3340.4406 | 412 | 138.2667 | 64.4 | 614.6667 | -2725.774 | FunT HC (15) moved to complete PHL FunT
Jan'28 | 19 | 173.9533 | 124 | 90% | 98.5% | 2974.602 | 968.2667 | 679.4667 | 151.2 | 1798.9333 | -1175.6687 | FunT HC (15) moved back to Production
Feb'28 | 21 | 171.344 | 122 | 90% | 98.5% | 3238.4023 | 1024.6667 | 255.2 | 160 | 1439.8667 | -1798.5356 | -
Mar'28 | 23 | 168.7739 | 121 | 90% | 98.5% | 3493.6192 | 1262.9333 | 345.3333 | 202 | 1810.2667 | -1683.3525 | -
Apr'28 | 19 | 166.2423 | 119 | 90% | 98.5% | 2842.7428 | 1459.3333 | 480.5333 | 228 | 2167.8667 | -674.8761 | -
May'28 | 22 | 163.7486 | 117 | 90% | 98.5% | 3242.2229 | 525.2 | 551.6 | 112.2667 | 1189.0667 | -2053.1563 | -
Jun'28 | 21 | 161.2924 | 115 | 90% | 98.5% | 3048.4264 | 689.3333 | 671.7333 | 173.7333 | 1534.8 | -1513.6264 | -
Jul'28 | 21 | 158.873 | 113 | 90% | 98.5% | 3002.7 | 724.9333 | 710.8 | 182.4 | 1618.1333 | -1384.5667 | -
Aug'28 | 22 | 156.4899 | 112 | 90% | 98.5% | 3098.5004 | 217.2 | 717.7333 | 54.6667 | 989.6 | -2108.9004 | -
Sep'28 | 20 | 154.1426 | 110 | 90% | 98.5% | 2774.5663 | 0 | 1607.7333 | 0 | 1607.7333 | -1166.833 | Tentative Indonesia completion time (2-Sep-28)
Oct'28 | 20 | 151.8304 | 108 | 90% | 98.5% | 2732.9478 | 0 | 1385.6 | 0 | 1385.6 | -1347.3478 | -
Nov'28 | 22 | 149.553 | 107 | 90% | 98.5% | 2961.149 | 0 | 529.0667 | 0 | 529.0667 | -2432.0823 | -
Dec'28 | 3 | 147.3097 | 105 | 90% | 98.5% | 397.7361 | 0 | 0 | 0 | 0 | -397.7361 | Tentative Philippines completion time (7-Dec-28)
[6 empty] | Overall | 16454.2667 | 33820.2667 | 2102.4 | Idle | -36772.7842
Pending effort | 52376.9333
Capacity available | 89149.7175
Idle Mandays | 36772.7842
[6 empty] | last week pending efforts | 106745
[6 empty] | Current week pending efforts | 104632
[6 empty] | Variance | 2113
[6 empty] | Week consumption | 1697
[6 empty] | Additionally lost effort due to Plan vs Actual & speed achievement | 547
[6 empty] | Overall variance | -131
#REF!

## HC Distribution
Year | Month | HLA | AdC | MPRA | Addressing Finishing (33) + FunT (15)+Aditional finishing(40) | Addressing Overall HC | Temporary Movement | Remarks
2025 | LTP 9/1 | 50 | 149.6 | 117 | 90 | 406.6
2025 | LTP 9/8 | 50 | 149.6 | 117 | 90 | 406.6 |  | Moving 42 HC (Additional) from Build to Finishing
2025 | LTP 9/15 | 50 | 149.6 | 117 | 90 | 406.6 |  | -
2025 | LTP 9/22 | 50 | 149.6 | 114 | 90 | 403.6 |  | -
2025 | LTP 9/29 | 50 | 149.6 | 114 | 90 | 403.6 |  | -
2025 | LTP 10/6 | 50 | 150 | 110 | 90 | 400 |  | -
2025 | LTP 10/13 | 50 | 150 | 110 | 90 | 400 |  | -
2025 | LTP 10/20 | 50 | 150 | 110 | 90 | 400 |  | -
2025 | LTP 10/27 | 50 | 150 | 110 | 90 | 400 |  | -
2025 | LTP 11/3 | 60 | 150 | 90 | 90 | 390 |  | -
2025 | LTP 11/10 | 60 | 150 | 90 | 90 | 390 |  | -
2025 | LTP 11/17 | 60 | 150 | 132 | 48 | 390 |  | -
2025 | LTP 11/24 | 60 | 150 | 132 | 48 | 390 |  | Bringing back 42 HC from Finishing to Build
2025 | LTP 12/1 | 50 | 150 | 152 | 33 | 385 |  | There is no FunT work planned beyond Nov'25; Hence 15 HC included in Production Dec'25 onwards
2025 | LTP 12/8 | 50 | 150 | 152 | 33 | 385 |  | There is no FunT work planned beyond Nov'25; Hence 15 HC included in Production Dec'25 onwards
2025 | LTP 12/15 | 50 | 150 | 152 | 33 | 385 |  | -
2025 | LTP 12/22 | 50 | 150 | 152 | 33 | 385 |  | -
2025 | LTP 12/29 | 50 | 150 | 152 | 33 | 385 |  | India Completed by 31-Dec-2025
2025 | LTP 1/5 | 40 | 150 | 157 | 33 | 380 |  | -
2025 | LTP 1/12 | 50 | 180 | 117 | 33 | 380 |  | -
2025 | LTP 1/19 | 50 | 180 | 117 | 33 | 380 |  | -
2026 | LTP 1/26 | 50 | 180 | 117 | 33 | 380 |  | -
2025 | LTP 2/2 | 80 | 180 | 82 | 33 | 375 |  | -
2025 | LTP 2/9 | 80 | 180 | 82 | 33 | 375 |  | -
2025 | LTP 2/16 | 50 | 120 | 176 | 33 | 379 |  | -
2025 | LTP 2/23 | 50 | 120 | 176 | 33 | 379
2026 | LTP 3/2 | 40 | 120 | 180 | 33 | 373 |  | -
2026 | LTP 3/9 | 40 | 120 | 180 | 33 | 373 |  | -
2026 | LTP 3/16 | 40 | 120 | 180 | 33 | 373 |  | -
2026 | LTP 3/23 | 40 | 120 | 180 | 33 | 373 |  | -
2026 | LTP 3/30 | 40 | 120 | 180 | 33 | 373 |  | -
2026 | LTP 4/6 | 40 | 80 | 215 | 33 | 368 |  | -
2026 | LTP 4/20 | 40 | 80 | 215 | 33 | 368 |  | -
2026 | LTP 4/27 | 40 | 80 | 215 | 33 | 368 |  | -
2026 | LTP 5/4 | 40 | 80 | 215 | 33 | 368 |  | -
2026 | LTP 5/11 | 50 | 225 | 0 | 33 | 308 |  | -
2026 | LTP 5/18 | 50 | 50 | 172 | 33 | 305 |  | -
2026 | LTP 5/25 | 50 | 50 | 172 | 33 | 305 |  | 57HC Movement, MPRA HC is engaged in IND product improvement
2026 | LTP 6/1 | 50 | 50 | 150 | 33 | 283 |  | 13HC Movement
2026 | LTP 6/8 | 25 | 50 | 171 | 33 | 279 |  | -
2026 | LTP 6/15 | 25 | 50 | 176 | 33 | 284 |  | 5 HC Added from Apple QA process to Addressing
2026 | LTP 6/22 | 25 | 50 | 156 | 33 | 264 |  | 20 HC moved for additional Finishing Task
2026 | LTP 6/29 | 25 | 50 | 156 | 33 | 264 |  | -
2026 | LTP 7/6 | 25 | 50 | 173 | 33 | 281 |  | -
2026 | LTP 7/13 | 25 | 50 | 120 | 33 | 228 |  | 20 HC moved to Additional Finishing Task 25 HC moved to QA temporarily
2026 | LTP 7/20 | 25 | 50 | 120 | 33 | 228 |  | 20 HC moved to Additional Finishing Task 25 HC moved to QA temporarily
2026 | LTP 7/27 | 25 | 50 | 120 | 33 | 228 | 25 | 20 HC moved to Additional Finishing Task 25 HC moved to QA temporarily
2026 | LTP 8/3 | 25 | 50 | 120 | 33 | 228 | 25 | -
2026 | LTP 8/10 | 25 | 50 | 107 | 53 | 235 | 25 | -
2026 | LTP 8/17 | 25 | 50 | 107 | 53 | 235 | 25 | -
2026 | LTP 8/24 | 25 | 50 | 107 | 53 | 235 | 25 | 20 HC movement extended for Additional Finishing Task 25 HC moved (Jul'26 to Sep'26) to QA temporarily
2026 | LTP 8/31 | 25 | 50 | 107 | 53 | 235 | 25 | 20 HC movement extended for Additional Finishing Task 25 HC moved (Jul'26 to Sep'26) to QA temporarily
2026 | LTP 9/7 | 25 | 50 | 101 | 53 | 229 | 25 | 20 HC movement extended for Additional Finishing Task 25 HC moved (Jul'26 to Sep'26) to QA temporarily
2026 | LTP 9/14 | 25 | 50 | 101 | 53 | 229 | 25 | 20 HC movement extended for Additional Finishing Task 25 HC moved (Jul'26 to Sep'26) to QA temporarily
2026 | LTP 9/21 | 15 | 30 | 51 | 93 | 189 | 65 | 20 HC movement extended for Additional Finishing Task & 40 HC for moved temporarily 25 HC moved (Jul'26 to Sep'26) to QA temporarily & 40 HC for Highway Service Road task
2026 | Sep | 15 | 30 | 51 | 93 | 189 | 65 | 20 HC movement extended for Additional Finishing Task & 40 HC for moved temporarily 25 HC moved (Jul'26 to Sep'26) to QA temporarily 40 HC for Highway Service Road task
2026 | Oct | 25 | 50 | 143 | 33 | 251 | - | 20 HC move back from Additional Finishing Task 25 HC move back from QA
2026 | Nov | 25 | 50 | 139 | 33 | 247 | - | -
2026 | Dec | 25 | 50 | 136 | 33 | 244 | - | 25HC kept aside for maintaining factory model HC (HLA 25HC)
2027 | Jan | 25 | 50 | 133 | 33 | 241 | - | 75HC kept aside for maintaining factory model HC (HLA 25HC and ADC 50HC)
2027 | Feb | 25 | 50 | 130 | 33 | 238 | - | -
2027 | Mar | 25 | 50 | 127 | 33 | 235 | - | -
2027 | Apr | 25 | 50 | 109 | 33 | 217 | - | -
2027 | May | 25 | 50 | 121 | 33 | 229 | - | -
2027 | Jun | 25 | 50 | 118 | 33 | 226 | - | Tentative Brazil Phase2 completion time (8-Jun-27) No inventory available for entire team post Brazil closure
2027 | Jul | 25 | 50 | 115 | 33 | 223 | - | Interim idle time every month till Philippines closure
2027 | Aug | 25 | 50 | 112 | 33 | 220 | -
2027 | Sep | 25 | 50 | 110 | 33 | 218 | -
2027 | Oct | 25 | 50 | 107 | 33 | 215 | -
2027 | Nov | 25 | 50 | 104 | 33 | 212 | -
2027 | Dec | 25 | 45 | 91 | 33 | 194 | -
2028 | Jan | 25 | 45 | 104 | 33 | 207 | -
2028 | Feb | 25 | 35 | 111 | 33 | 204 | -
2028 | Mar | 25 | 35 | 109 | 33 | 202 | -
2028 | Apr | 25 | 25 | 116 | 33 | 199 | -
2028 | May | 25 | 25 | 114 | 33 | 197 | -
2028 | Jun | 25 | 25 | 111 | 33 | 194 | -
2028 | Jul | 25 | 25 | 109 | 33 | 192 | -
2028 | Aug | 25 | 25 | 106 | 33 | 189 | -
2028 | Sep | 25 | 25 | 104 | 33 | 187 | - | 25HC kept aside for maintaining factory model HC (HLA 25HC), Tentative Indonesia completion time (2-Sep-28)
2028 | Oct | 25 | 25 | 102 | 33 | 185 | - | 50HC kept aside for maintaining factory model HC (HLA 25HC and ADC 25HC)
2028 | Nov | 25 | 25 | 100 | 33 | 183 | - | -
2028 | Dec | 25 | 25 | 97 | 33 | 180 | - | Tentative Philippines completion time (7-Dec-28) As on date , No Future markets in pipeline

## Inventory
Last updated Date | 2026-09-21
|  |  |  | In Pipeline from Upstream (Naming QA & DC2) | [5 empty] | Abbreviations | Definition | Status | Band (in days) | Flag
Category | In Hand | Pre-Rx | In Pipeline | Current Week (9/20 - 9/26) | Current Week +1 (9/27 - 10/3) | Current Week +2 (10/4 - 10/10) | Current Week +3 (10/11 - 10/17) |  |  | WIP | Waves In Progress | WIP | >2 | Green
Mandays | 2170 | 5450 | 3792 | 0 | 0 | 1507 | 2285 |  |  | YTS | Waves generated & yet to be picked |  | >1 - <=2 | White
Workdays | 9.819 | 24.6606 | 17.1584 | 0 | 0 | 6.819 | 10.3394 |  |  | In Hand | Total work in BRs available from upstream (depends on jobrun) |  | >0.5 - <=1 | Amber
[10 empty] | In Hand- Blocked | Work Available till phase end for the Blocked Waves (Due to Job issues / source unavailabilty) |  | <=0.5 | Red
HC | 221 | [8 empty] | Current Week (Date range) | Work expected from Naming QA and DCLG in the current Week
100% Utilization till (In Hand + Pre-Rx) | 2026-11-05 | [8 empty] | Current Week +1 (Date range) | Work expected from Naming QA and DCLG in the upcoming Week
[10 empty] | Current Week +2 (Date range) | Work expected from Naming QA and DCLG in the upcoming 2nd week
WIP & YTS BRs | [9 empty] | Current Week +3 (Date range) | Work expected from Naming QA and DCLG in the upcoming 3rd week
Region | BR ID | BR | WIP wave | Dependencies (If Any) | WIP (Effort in Man-days) | Effort pending till end of BV (In Man days)
MPRA
Brazil_P2 | kh.br.sa.bra.08_A | São Paulo | MPRA BV ITR2 | WIP | 9 | 0
Brazil_P2 | kh.br.sa.bra.11_A | Rio de Janeiro | Resnap HLA | WIP | 1 | 395
Brazil_P2 | kh.br.sa.bra.11_C | Vitória | Ranges2 | WIP | 180 | 300
Brazil_P2 | kh.br.sa.bra.11_B | Campos dos Goytacazes | Ranges2 | WIP | 307 | 615
Brazil_P2 | kh.br.sa.bra.08_C | Campinas | Ranges2 | WIP | 232 | 739
Brazil_P2 | kh.br.sa.bra.08_D | Ribeirão Preto | Merge | YTS | 43 | 1474
Brazil_P2 | kh.br.sa.bra.08_B | São José dos Campos | Merge | JIP | 58 | 1546
Total |  |  |  |  | 830 | 5069
HLA & ADC
Brazil_P2 | kh.br.sa.bra.06 | Porto Alegre | Unmatched | YTS | 794 | 209
Brazil_P2 | kh.br.sa.bra.04 | Cuiaba | Unmatched | YTS | 236 | 57
Brazil_P2 | kh.br.sa.bra.03 | Belem | HLA | YTS | 283 | 81
Brazil_P2 | kh.br.sa.bra.02 | Manaus | HLA | YTS | 27 | 34
Total |  |  |  |  | 1340 | 381
Expected per Plan (Naming QA & DC2)
Region | BR ID | BR | Blocked Wave | Dependencies (If Any) | WIP (Effort in Man-days) | Effort pending till end of BV (In Man days) | Expected Date | Week Range | Remarks
Brazil_P2 | kh.br.sa.bra.07_A | Curitiba | HLA & AdC Stage | Naming QA | - | 1271 | 2026-10-17 | Current Week +3 (10/11 - 10/17) | -
Brazil_P2 | kh.br.sa.bra.16 | Salvador | MPRA Stage | DC2 | - | 1507 | 2026-10-04 | Current Week +2 (10/4 - 10/10) | -
Brazil_P2 | kh.br.sa.bra.17 | Recife | MPRA Stage | DC2 | - | 1014 | 2026-10-12 | Current Week +3 (10/11 - 10/17) | -

## Wave wise Effort
°–
[15 empty] | Region | Source Prep (mandays) | HLA (mandays) | ADC (mandays) | MPRA (mandays) | Overall Pending Effort (Mandays) |  | Region | Source Prep (hours) | HLA (hours) | ADC (hours) | MPRA (hours) | Overall Pending Effort (hours)
WIP | [14 empty] | Brazil_P2 | 0 | 562 | 3489.7333 | 25647.0667 | 29698.8 |  | Brazil_P2 | 0 | 4215 | 26173 | 192353 | 222741
YTS | [14 empty] | Indonesia | 1599.4667 | 4555.6 | 5685.2 | 4092.8 | 15933.0667 |  | Indonesia | 11996 | 34167 | 42639 | 30696 | 119498
Completed | [14 empty] | Philippines | 502.9333 | 962.1333 | 1035.0667 | 4061.3333 | 6561.4667 |  | Philippines | 3772 | 7216 | 7763 | 30460 | 49211
JIP | [14 empty] | Vietnam_P2 | 0 | 0 | 0 | 0 | 0 |  | Vietnam_P2 | 0 | 0 | 0 | 0 | 0
Blocked | [14 empty] | Moldova | 0 | 0 | 0 | 0 | 0 |  | Moldova | 0 | 0 | 0 | 0 | 0
Awaiting Source | [14 empty] | Overall | 2102.4 | 6079.7333 | 10210 | 33801.2 | 52193.3333 |  | Overall | 15768 | 45598 | 76575 | 253509 | 391450
COUNTRY | DR | Combo | BR_ID | BR_Name | Naming QA Acceptance | DC2 | Current Stage | Current Status | Current Wave | Source Prep | HLA | ADC | MPRA | Finishing | Source Prep | Hookline | HLA-BV | Unmatched | Unexplained | Duplicate Cleanup | Anamolies Cleanup | ADC-AA | AC-BV | Ranges1 | Ranges2 | Access Point | Merge | CopyRanges | AP Validation | RAP/ Deduce AP | Re-SNAP HLA | PFA | Cluster DeDup | MPRA BV | MPRA-AA | Final BV - Build Breaker | Ap Validation of large building | PFA Validation | Source Prep | HLA | ADC | MPRA
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_A | kh.br.sa.bra.08_A | São Paulo | 2025-12-31 | 2026-06-20 | MPRA | WIP | Final BV - Build Breaker |  |  |  | 10 | [22 empty] | 75 |  |  | 0 | 0 | 0 | 75 | 75 | 0 | São Paulo | 9 | 0
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_C | kh.br.sa.bra.08_C | Campinas | 2026-01-07 | 2026-08-09 | MPRA | WIP | Ranges2 |  |  |  | 1181.8667 | [11 empty] | 1936 | 1590 |  |  |  | 8 | 150 | 204 | 120 | 3702 | 229 | 925 |  |  | 0 | 0 | 0 | 8864 | 1936 | 6928 | Campinas | 232.32 | 738.9867
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_D | kh.br.sa.bra.08_D | Ribeirão Preto | 2026-01-19 | 2026-09-06 | MPRA | YTS | Merge |  |  |  | 1890.8 | [10 empty] | 6 | 6872 | 1832 | 361 |  |  | 8 | 173 | 209 | 138 | 3481 | 231 | 870 |  |  | 0 | 0 | 0 | 14181 | 361 | 13820 | Ribeirão Preto | 43.32 | 1474.1333
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_B | kh.br.sa.bra.08_B | São José dos Campos | 2026-01-27 | 2026-09-18 | MPRA | YTS | Merge |  |  |  | 1996.9333 | [10 empty] | 22 | 6234 | 1776 | 482 |  |  | 9 | 167 | 227 | 134 | 4537 | 255 | 1134 |  |  | 0 | 0 | 0 | 14977 | 482 | 14495 | São José dos Campos | 57.84 | 1546.1333
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_A | kh.br.sa.bra.11_A | Rio de Janeiro | 2026-01-29 | 2026-07-07 | MPRA | WIP | MPRA BV |  |  |  | 479.0667 | [19 empty] | 80 | 2713 | 122 | 678 |  |  | 0 | 0 | 0 | 3593 | 0 | 3593 | Rio de Janeiro | 0 | 383.2533
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_B | kh.br.sa.bra.11_B | Campos dos Goytacazes | 2026-01-31 | 2026-07-12 | MPRA | WIP | Ranges2 |  |  |  | 1110.5333 | [11 empty] | 2560 | 1253 |  |  |  | 5 | 118 | 141 | 95 | 3201 | 156 | 800 |  |  | 0 | 0 | 0 | 8329 | 2560 | 5769 | Campos dos Goytacazes | 307.2 | 615.36
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_C | kh.br.sa.bra.11_C | Vitória | 2026-02-06 | 2026-07-21 | MPRA | WIP | Ranges2 |  |  |  | 575.2 | [11 empty] | 1498 | 609 |  |  |  | 3 | 57 | 74 | 46 | 1555 | 83 | 389 |  |  | 0 | 0 | 0 | 4314 | 1498 | 2816 | Vitória | 179.76 | 300.3733
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.16 | kh.br.sa.bra.16 | Salvador | 2026-02-22 | 2026-10-04 | MPRA | Awaiting Source | - |  |  |  | 1507.0667 | [10 empty] | 15 | 4337 | 1236 | 335 |  |  | 3 | 116 | 261 | 93 | 3157 | 961 | 789 |  |  | 0 | 0 | 0 | 11303
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.17 | kh.br.sa.bra.17 | Recife | 2026-03-10 | 2026-10-12 | MPRA | Awaiting Source | - |  |  |  | 1014.4 | [13 empty] | 444 | 969 | 270 | 7 | 154 | 197 | 123 | 4179 | 220 | 1045 |  |  | 0 | 0 | 0 | 7608
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.18 | kh.br.sa.bra.18 | Natal | 2026-04-02 | 2026-10-21 | MPRA | Awaiting Source | - |  |  |  | 568.4 | [13 empty] | 250 | 273 | 152 | 5 | 87 | 157 | 69 | 2349 | 334 | 587 |  |  | 0 | 0 | 0 | 4263
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.13 | kh.br.sa.bra.13 | Sao Luis | 2026-03-23 | 2026-10-25 | MPRA | Awaiting Source | - |  |  |  | 304.8 | [13 empty] | 122 | 133 | 74 | 1 | 42 | 95 | 34 | 1147 | 351 | 287 |  |  | 0 | 0 | 0 | 2286
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.14 | kh.br.sa.bra.14 | Teresina | 2026-03-24 | 2026-10-28 | MPRA | Awaiting Source | - |  |  |  | 233.0667 | [13 empty] | 92 | 100 | 56 | 1 | 32 | 77 | 25 | 863 | 286 | 216 |  |  | 0 | 0 | 0 | 1748
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.15 | kh.br.sa.bra.15 | Fortaleza | 2026-04-23 | 2026-11-07 | MPRA | Awaiting Source | - |  |  |  | 582.6667 | [13 empty] | 261 | 311 | 68 | 5 | 91 | 159 | 72 | 2454 | 335 | 614 |  |  | 0 | 0 | 0 | 4370
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.12 | kh.br.sa.bra.12 | Palmas | 2026-05-06 | 2026-11-12 | MPRA | Awaiting Source | - |  |  |  | 115.8667 | [13 empty] | 46 | 55 | 12 | 1 | 16 | 39 | 13 | 433 | 146 | 108 |  |  | 0 | 0 | 0 | 869
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.10_B | kh.br.sa.bra.10_B | Uberlândia | 2026-03-17 | 2026-11-28 | MPRA | Awaiting Source | - |  |  |  | 2746.1333 | [10 empty] | 29 | 8350 | 2379 | 646 |  |  | 13 | 224 | 380 | 179 | 6078 | 799 | 1519 |  |  | 0 | 0 | 0 | 20596
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.10_A | kh.br.sa.bra.10_A | Belo Horizonte | 2026-05-13 | 2026-12-13 | MPRA | Awaiting Source | - |  |  |  | 1369.3333 | [13 empty] | 512 | 594 | 133 | 10 | 178 | 311 | 142 | 6186 | 657 | 1547 |  |  | 0 | 0 | 0 | 10270
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.09_B | kh.br.sa.bra.09_B | Goiânia | 2026-06-28 | 2026-12-27 | MPRA | Awaiting Source | - |  |  |  | 1339.8667 | [10 empty] | 14 | 4052 | 1154 | 313 |  |  | 3 | 109 | 154 | 87 | 2949 | 477 | 737 |  |  | 0 | 0 | 0 | 10049
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.09_A | kh.br.sa.bra.09_A | Brasília | 2026-07-09 | 2027-01-02 | MPRA | Awaiting Source | - |  |  |  | 548.1333 | [10 empty] | 3 | 938 | 2013 | 73 |  |  | 1 | 25 | 44 | 20 | 683 | 140 | 171 |  |  | 0 | 0 | 0 | 4111
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.07_A | kh.br.sa.bra.07_A | Curitiba | 2026-10-17 | 2027-01-17 | HLA | Awaiting Source | - |  | 86.5333 | 1184.5333 | 1969.6 |  |  | 644 | 5 | 7574 | 1 | 646 | 126 | 201 | 336 | 21 | 6008 | 1712 | 465 |  |  | 9 | 161 | 260 | 129 | 4373 | 541 | 1093 |  |  | 0 | 649 | 8884 | 14772
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.06 | kh.br.sa.bra.06 | Porto Alegre | 2026-07-30 | 2027-01-27 | ADC | YTS | Unmatched |  |  | 1143.4667 | 1914.1333 |  |  |  |  | 6615 | 1 | 624 | 122 | 194 | 1020 | 20 | 5804 | 1654 | 449 |  |  | 9 | 156 | 276 | 125 | 4225 | 582 | 1056 |  |  | 0 | 0 | 8576 | 14356 | 6615 | 1961 | Porto Alegre | 793.8 | 209.1733
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.05 | kh.br.sa.bra.05 | Corumba | 2026-08-11 | 2027-02-01 | MPRA | Awaiting Source | - |  |  | 0 | 549.8667 | [10 empty] | 6 | 1614 | 460 | 125 |  |  | 1 | 43 | 81 | 35 | 1174 | 291 | 294 |  |  | 0 | 0 | 0 | 4124
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.07_B | kh.br.sa.bra.07_B | Joinville | 2026-11-24 | 2027-02-09 | HLA | Awaiting Source | - |  | 246 | 732 | 1124.8 |  |  | 1808 | 37 | 4330 | 0 | 369 | 72 | 115 | 604 | 12 | 3434 | 978 | 266 |  |  | 5 | 92 | 146 | 74 | 2500 | 304 | 625 |  |  | 0 | 1845 | 5490 | 8436
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.04 | kh.br.sa.bra.04 | Cuiaba | 2026-08-19 | 2027-02-16 | ADC | YTS | Unmatched |  |  | 316.5333 | 872.6667 |  |  |  |  | 1834 | 1 | 115 | 164 | 15 | 245 | 9 | 1638 | 1026 | 278 |  |  | 1 | 97 | 105 | 77 | 2346 | 381 | 587 |  |  | 0 | 0 | 2374 | 6545 | 1834 | 540 | Cuiaba | 220.08 | 57.6
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.01 | kh.br.sa.bra.01 | Porto Velho | 2026-08-25 | 2027-02-17 | MPRA | Awaiting Source | - |  |  | 0 | 389.3333 | [10 empty] | 4 | 1121 | 319 | 87 |  |  | 1 | 30 | 67 | 24 | 816 | 247 | 204 |  |  | 0 | 0 | 0 | 2920
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.03 | kh.br.sa.bra.03 | Belem | 2026-09-07 | 2027-02-19 | HLA | WIP | Hookline |  | 229.4667 | 95.7333 | 740.5333 |  |  | 1675 | 46 |  |  | 229 | 43 | 71 | 375 | 7 | 2134 | 608 | 165 |  |  | 2 | 57 | 127 | 46 | 1554 | 466 | 388 |  |  | 0 | 1721 | 718 | 5554 | 1675 | 764 | Belem | 201 | 81.4933
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.02 | kh.br.sa.bra.02 | Manaus | 2026-09-11 | 2027-02-19 | ADC | WIP | Anamolies Cleanup |  | 0 | 17.4667 | 512 | [7 empty] | 0 | 49 | 82 | 5 | 1461 | 416 | 113 |  |  | 1 | 39 | 94 | 31 | 1063 | 351 | 266 |  |  | 0 | 0 | 131 | 3840 | 0 | 131 | Manaus | 0 | 13.9733
Indonesia | IDDRSM | Indonesiakh.br.as.idn.01 | kh.br.as.idn.01 | Aceh | 2027-07-26 | 2027-11-28 | Source Prep | Awaiting Source | - | 31.6 | 90.1333 | 112.4 | 81.0667 |  | 237 | 633 | 43 | 583 | 5 | 74 | 75 | 45 | 61 | 16 | 176 | 117 | 58 | 35 | 4 | 0 | 18 | 7 | 8 | 158 | 11 |  |  |  | 237 | 676 | 843 | 608
Indonesia | IDDRSM | Indonesiakh.br.as.idn.05 | kh.br.as.idn.05 | Lampung | 2027-08-28 | 2027-12-18 | Source Prep | Awaiting Source | - | 54 | 154 | 192.1333 | 138.2667 |  | 405 | 1081 | 74 | 996 | 8 | 127 | 129 | 77 | 104 | 27 | 300 | 200 | 100 | 60 | 6 | 0 | 30 | 12 | 14 | 270 | 18 |  |  |  | 405 | 1155 | 1441 | 1037
Indonesia | IDDRSM | Indonesiakh.br.as.idn.04 | kh.br.as.idn.04 | Sumatra Island South | 2027-09-09 | 2028-01-02 | Source Prep | Awaiting Source | - | 92.9333 | 264.6667 | 330.4 | 237.4667 |  | 697 | 1858 | 127 | 1711 | 15 | 219 | 221 | 133 | 179 | 46 | 516 | 344 | 171 | 103 | 11 | 0 | 52 | 20 | 23 | 464 | 31 |  |  |  | 697 | 1985 | 2478 | 1781
Indonesia | IDDRSM | Indonesiakh.br.as.idn.03 | kh.br.as.idn.03 | Sumatra Island Central | 2027-09-21 | 2028-01-14 | Source Prep | Awaiting Source | - | 84 | 239.0667 | 298.5333 | 214.8 |  | 630 | 1679 | 114 | 1547 | 13 | 198 | 200 | 120 | 161 | 42 | 466 | 311 | 155 | 93 | 10 | 0 | 47 | 18 | 21 | 420 | 28 |  |  |  | 630 | 1793 | 2239 | 1611
Indonesia | IDDRSM | Indonesiakh.br.as.idn.02 | kh.br.as.idn.02 | Medan | 2027-09-29 | 2028-01-28 | Source Prep | Awaiting Source | - | 88.8 | 252.9333 | 315.7333 | 227.2 |  | 666 | 1776 | 121 | 1636 | 14 | 209 | 211 | 127 | 171 | 44 | 493 | 329 | 164 | 99 | 11 | 0 | 49 | 19 | 22 | 444 | 30 |  |  |  | 666 | 1897 | 2368 | 1704
Indonesia | IDDRKA | Indonesiakh.br.as.idn.07 | kh.br.as.idn.07 | West Kalimantan | 2027-10-03 | 2028-02-11 | Source Prep | Awaiting Source | - | 48.5333 | 138.1333 | 172.4 | 124.1333 |  | 364 | 970 | 66 | 894 | 8 | 114 | 115 | 69 | 93 | 24 | 269 | 180 | 89 | 54 | 6 | 0 | 27 | 11 | 12 | 243 | 16 |  |  |  | 364 | 1036 | 1293 | 931
Indonesia | IDDRKA | Indonesiakh.br.as.idn.06 | kh.br.as.idn.06 | East Kalimantan | 2027-10-06 | 2028-02-22 | Source Prep | Awaiting Source | - | 51.2 | 146 | 182.2667 | 131.0667 |  | 384 | 1025 | 70 | 944 | 8 | 121 | 122 | 73 | 99 | 26 | 285 | 190 | 94 | 57 | 6 | 0 | 28 | 11 | 13 | 256 | 17 |  |  |  | 384 | 1095 | 1367 | 983
Indonesia | IDDRJW | Indonesiakh.br.as.idn.09 | kh.br.as.idn.09 | Jakarta | 2027-10-14 | 2028-03-03 | Source Prep | Awaiting Source | - | 63.3333 | 180.5333 | 225.3333 | 162.2667 |  | 475 | 1268 | 86 | 1167 | 10 | 149 | 151 | 91 | 122 | 32 | 352 | 235 | 117 | 70 | 8 | 0 | 35 | 14 | 16 | 317 | 21 |  |  |  | 475 | 1354 | 1690 | 1217
Indonesia | IDDRJW | Indonesiakh.br.as.idn.08 | kh.br.as.idn.08 | Banten | 2027-10-24 | 2028-03-23 | Source Prep | Awaiting Source | - | 71.4667 | 203.4667 | 253.8667 | 183.0667 |  | 536 | 1429 | 97 | 1316 | 11 | 168 | 170 | 102 | 137 | 36 | 397 | 265 | 132 | 79 | 9 | 0 | 40 | 16 | 18 | 357 | 24 |  |  |  | 536 | 1526 | 1904 | 1373
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_A | kh.br.as.idn.10_A | West Java A | 2027-11-12 | 2028-04-08 | Source Prep | Awaiting Source | - | 103.6 | 294.9333 | 368 | 265.0667 |  | 777 | 2071 | 141 | 1907 | 16 | 244 | 246 | 148 | 199 | 52 | 575 | 383 | 191 | 115 | 12 | 0 | 58 | 23 | 26 | 518 | 35 |  |  |  | 777 | 2212 | 2760 | 1988
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_C | kh.br.as.idn.12_C | East Java C | 2027-11-29 | 2028-04-24 | Source Prep | Awaiting Source | - | 84.2667 | 239.8667 | 299.3333 | 215.4667 |  | 632 | 1684 | 115 | 1551 | 13 | 198 | 201 | 120 | 162 | 42 | 468 | 312 | 155 | 94 | 10 | 0 | 47 | 18 | 21 | 421 | 28 |  |  |  | 632 | 1799 | 2245 | 1616
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_C | kh.br.as.idn.11_C | Yogyakarta | 2027-12-17 | 2028-05-07 | Source Prep | Awaiting Source | - | 64.4 | 183.3333 | 228.6667 | 164.5333 |  | 483 | 1287 | 88 | 1185 | 10 | 151 | 153 | 92 | 124 | 32 | 357 | 238 | 119 | 71 | 8 | 0 | 36 | 14 | 16 | 322 | 21 |  |  |  | 483 | 1375 | 1715 | 1234
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_B | kh.br.as.idn.12_B | East Java B | 2028-01-07 | 2028-05-18 | Source Prep | Awaiting Source | - | 83.3333 | 237.4667 | 296.2667 | 213.4667 |  | 625 | 1667 | 114 | 1536 | 13 | 196 | 198 | 119 | 160 | 42 | 463 | 309 | 154 | 93 | 10 | 0 | 46 | 18 | 21 | 417 | 28 |  |  |  | 625 | 1781 | 2222 | 1601
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_B | kh.br.as.idn.11_B | Central Java B | 2028-01-23 | 2028-05-28 | Source Prep | Awaiting Source | - | 67.8667 | 193.2 | 241.3333 | 173.6 |  | 509 | 1357 | 92 | 1250 | 11 | 160 | 162 | 97 | 130 | 34 | 377 | 251 | 125 | 75 | 8 | 0 | 38 | 15 | 17 | 339 | 23 |  |  |  | 509 | 1449 | 1810 | 1302
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_A | kh.br.as.idn.12_A | East Java A | 2028-02-08 | 2028-06-10 | Source Prep | Awaiting Source | - | 76.4 | 217.6 | 271.7333 | 195.4667 |  | 573 | 1528 | 104 | 1408 | 12 | 180 | 182 | 109 | 147 | 38 | 425 | 283 | 141 | 85 | 9 | 0 | 42 | 17 | 19 | 382 | 25 |  |  |  | 573 | 1632 | 2038 | 1466
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_C | kh.br.as.idn.10_C | West Java C | 2028-02-22 | 2028-06-20 | Source Prep | Awaiting Source | - | 83.6 | 238.1333 | 297.2 | 213.8667 |  | 627 | 1672 | 114 | 1540 | 13 | 197 | 199 | 119 | 161 | 42 | 464 | 310 | 154 | 93 | 10 | 0 | 46 | 18 | 21 | 418 | 28 |  |  |  | 627 | 1786 | 2229 | 1604
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_B | kh.br.as.idn.10_B | West Java B | 2028-03-08 | 2028-06-30 | Source Prep | Awaiting Source | - | 102.5333 | 292 | 364.4 | 262.4 |  | 769 | 2050 | 140 | 1889 | 16 | 241 | 244 | 146 | 197 | 51 | 570 | 380 | 189 | 114 | 12 | 0 | 57 | 22 | 26 | 513 | 34 |  |  |  | 769 | 2190 | 2733 | 1968
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_A | kh.br.as.idn.11_A | Central Java A | 2028-03-23 | 2028-07-09 | Source Prep | Awaiting Source | - | 86.9333 | 247.7333 | 309.0667 | 222.5333 |  | 652 | 1739 | 119 | 1601 | 14 | 205 | 207 | 124 | 167 | 44 | 483 | 322 | 160 | 97 | 10 | 0 | 48 | 19 | 22 | 435 | 29 |  |  |  | 652 | 1858 | 2318 | 1669
Indonesia | IDDRSL | Indonesiakh.br.as.idn.14 | kh.br.as.idn.14 | Celebes South | 2028-04-07 | 2028-07-21 | Source Prep | Awaiting Source | - | 78.6667 | 224.1333 | 279.6 | 201.3333 |  | 590 | 1574 | 107 | 1450 | 12 | 185 | 187 | 112 | 151 | 39 | 437 | 292 | 145 | 87 | 9 | 0 | 44 | 17 | 20 | 394 | 26 |  |  |  | 590 | 1681 | 2097 | 1510
Indonesia | IDDRSL | Indonesiakh.br.as.idn.13 | kh.br.as.idn.13 | Celebes North | 2028-04-11 | 2028-07-24 | Source Prep | Awaiting Source | - | 40.6667 | 115.8667 | 144.5333 | 104.1333 |  | 305 | 814 | 55 | 749 | 6 | 96 | 97 | 58 | 78 | 20 | 226 | 151 | 75 | 45 | 5 | 0 | 23 | 9 | 10 | 203 | 14 |  |  |  | 305 | 869 | 1084 | 781
Indonesia | IDDRNU | Indonesiakh.br.as.idn.16 | kh.br.as.idn.16 | East Nusa Tenggara | 2028-04-17 | 2028-07-29 | Source Prep | Awaiting Source | - | 32 | 91.0667 | 113.6 | 82 |  | 240 | 639 | 44 | 589 | 5 | 75 | 76 | 46 | 61 | 16 | 178 | 118 | 59 | 36 | 4 | 0 | 18 | 7 | 8 | 160 | 11 |  |  |  | 240 | 683 | 852 | 615
Indonesia | IDDRNU | Indonesiakh.br.as.idn.15 | kh.br.as.idn.15 | Bali | 2028-04-27 | 2028-08-04 | Source Prep | Awaiting Source | - | 57.8667 | 164.8 | 205.6 | 147.8667 |  | 434 | 1157 | 79 | 1065 | 9 | 136 | 138 | 83 | 111 | 29 | 321 | 214 | 107 | 64 | 7 | 0 | 32 | 13 | 14 | 289 | 19 |  |  |  | 434 | 1236 | 1542 | 1109
Indonesia | IDDRML | Indonesiakh.br.as.idn.18 | kh.br.as.idn.18 | North Maluku | 2028-04-28 | 2028-08-05 | Source Prep | Awaiting Source | - | 7.7333 | 21.8667 | 27.3333 | 20 |  | 58 | 154 | 10 | 142 | 1 | 18 | 18 | 11 | 15 | 4 | 43 | 29 | 14 | 9 | 1 | 0 | 4 | 2 | 2 | 39 | 3 |  |  |  | 58 | 164 | 205 | 150
Indonesia | IDDRML | Indonesiakh.br.as.idn.17 | kh.br.as.idn.17 | Maluku | 2028-04-29 | 2028-08-06 | Source Prep | Awaiting Source | - | 11.0667 | 31.6 | 39.3333 | 28.2667 |  | 83 | 222 | 15 | 204 | 2 | 26 | 26 | 16 | 21 | 6 | 62 | 41 | 20 | 12 | 1 | 0 | 6 | 2 | 3 | 55 | 4 |  |  |  | 83 | 237 | 295 | 212
Indonesia | IDDRPP | Indonesiakh.br.as.idn.20 | kh.br.as.idn.20 | Papua East | 2028-05-01 | 2028-08-08 | Source Prep | Awaiting Source | - | 17.4667 | 49.8667 | 62.2667 | 44.6667 |  | 131 | 350 | 24 | 322 | 3 | 41 | 42 | 25 | 34 | 9 | 97 | 65 | 32 | 19 | 2 | 0 | 10 | 4 | 4 | 87 | 6 |  |  |  | 131 | 374 | 467 | 335
Indonesia | IDDRPP | Indonesiakh.br.as.idn.19 | kh.br.as.idn.19 | Papua West | 2028-05-03 | 2028-08-10 | Source Prep | Awaiting Source | - | 15.2 | 43.2 | 53.8667 | 38.8 |  | 114 | 303 | 21 | 279 | 2 | 36 | 36 | 22 | 29 | 8 | 84 | 56 | 28 | 17 | 2 | 0 | 8 | 3 | 4 | 76 | 5 |  |  |  | 114 | 324 | 404 | 291
Philippines | PHDR2 | Philippineskh.br.as.phl.08 | kh.br.as.phl.08 | Mimaropa | 2028-03-26 | 2028-07-13 | Source Prep | Awaiting Source | - | 12.5333 | 23.8667 | 25.8667 | 100.8 |  | 94 | 169 | 10 | 106 | 5 | 26 | 25 | 24 | 8 | 1 | 210 | 271 | 108 |  |  | 0 | 40 | 2 | 7 | 87 | 30 |  |  |  | 94 | 179 | 194 | 756
Philippines | PHDR2 | Philippineskh.br.as.phl.09 | kh.br.as.phl.09 | Western Visayas | 2028-05-07 | 2028-08-14 | Source Prep | Awaiting Source | - | 18.2667 | 34.9333 | 37.6 | 147.6 |  | 137 | 247 | 15 | 155 | 7 | 37 | 37 | 35 | 11 | 2 | 308 | 397 | 158 |  |  | 0 | 59 | 3 | 10 | 127 | 43 |  |  |  | 137 | 262 | 282 | 1107
Philippines | PHDR2 | Philippineskh.br.as.phl.18 | kh.br.as.phl.18 | Negros Island | 2028-05-12 | 2028-08-20 | Source Prep | Awaiting Source | - | 18.4 | 35.2 | 38 | 148.6667 |  | 138 | 249 | 15 | 156 | 7 | 38 | 37 | 35 | 12 | 2 | 310 | 400 | 159 |  |  | 0 | 59 | 3 | 10 | 128 | 44 |  |  |  | 138 | 264 | 285 | 1115
Philippines | PHDR2 | Philippineskh.br.as.phl.11 | kh.br.as.phl.11 | Eastern Visayas | 2028-05-15 | 2028-08-23 | Source Prep | Awaiting Source | - | 17.6 | 33.6 | 36.1333 | 141.8667 |  | 132 | 238 | 14 | 149 | 7 | 36 | 35 | 33 | 11 | 2 | 296 | 382 | 152 |  |  | 0 | 56 | 2 | 10 | 122 | 42 |  |  |  | 132 | 252 | 271 | 1064
Philippines | PHDR2 | Philippineskh.br.as.phl.10 | kh.br.as.phl.10 | Central Visayas | 2028-05-24 | 2028-09-03 | Source Prep | Awaiting Source | - | 25.3333 | 48.4 | 52.1333 | 204.4 |  | 190 | 342 | 21 | 214 | 10 | 52 | 51 | 48 | 16 | 3 | 426 | 550 | 219 |  |  | 0 | 81 | 4 | 14 | 176 | 60 |  |  |  | 190 | 363 | 391 | 1533
Philippines | PHDR1 | Philippineskh.br.as.phl.06 | kh.br.as.phl.06 | Manila | 2028-06-04 | 2028-09-11 | Source Prep | Awaiting Source | - | 78.2667 | 149.6 | 160.8 | 631.6 |  | 587 | 1058 | 64 | 662 | 30 | 160 | 157 | 148 | 49 | 9 | 1317 | 1699 | 676 |  |  | 0 | 250 | 11 | 44 | 545 | 186 |  |  |  | 587 | 1122 | 1206 | 4737
Philippines | PHDR1 | Philippineskh.br.as.phl.07 | kh.br.as.phl.07 | Bicol | 2028-06-09 | 2028-09-13 | Source Prep | Awaiting Source | - | 23.4667 | 44.9333 | 48.2667 | 189.8667 |  | 176 | 318 | 19 | 199 | 9 | 48 | 47 | 44 | 15 | 3 | 396 | 511 | 203 |  |  | 0 | 75 | 3 | 13 | 164 | 56 |  |  |  | 176 | 337 | 362 | 1424
Philippines | PHDR1 | Philippineskh.br.as.phl.04 | kh.br.as.phl.04 | Central Luzon | 2028-06-22 | 2028-09-28 | Source Prep | Awaiting Source | - | 72 | 137.7333 | 148 | 581.8667 |  | 540 | 974 | 59 | 610 | 28 | 147 | 144 | 136 | 45 | 8 | 1214 | 1565 | 622 |  |  | 0 | 231 | 10 | 41 | 502 | 171 |  |  |  | 540 | 1033 | 1110 | 4364
Philippines | PHDR1 | Philippineskh.br.as.phl.05 | kh.br.as.phl.05 | Calabarzon | 2028-07-10 | 2028-10-14 | Source Prep | Awaiting Source | - | 93.8667 | 179.6 | 193.2 | 758.4 |  | 704 | 1270 | 77 | 796 | 37 | 192 | 188 | 177 | 59 | 10 | 1582 | 2040 | 812 |  |  | 0 | 301 | 13 | 53 | 654 | 223 |  |  |  | 704 | 1347 | 1449 | 5688
Philippines | PHDR1 | Philippineskh.br.as.phl.02 | kh.br.as.phl.02 | Cordillera | 2028-07-11 | 2028-10-15 | Source Prep | Awaiting Source | - | 6.9333 | 13.3333 | 14.2667 | 56 |  | 52 | 94 | 6 | 59 | 3 | 14 | 14 | 13 | 4 | 1 | 117 | 151 | 60 |  |  | 0 | 22 | 1 | 4 | 48 | 16 |  |  |  | 52 | 100 | 107 | 420
Philippines | PHDR1 | Philippineskh.br.as.phl.03 | kh.br.as.phl.03 | Cagayan Valley | 2028-07-14 | 2028-10-19 | Source Prep | Awaiting Source | - | 14.2667 | 27.3333 | 29.4667 | 115.2 |  | 107 | 193 | 12 | 121 | 6 | 29 | 29 | 27 | 9 | 2 | 240 | 310 | 123 |  |  | 0 | 46 | 2 | 8 | 99 | 34 |  |  |  | 107 | 205 | 221 | 864
Philippines | PHDR1 | Philippineskh.br.as.phl.01 | kh.br.as.phl.01 | Ilocos | 2028-07-20 | 2028-10-23 | Source Prep | Awaiting Source | - | 20.5333 | 39.2 | 42.2667 | 165.6 |  | 154 | 277 | 17 | 174 | 8 | 42 | 41 | 39 | 13 | 2 | 345 | 445 | 177 |  |  | 0 | 66 | 3 | 12 | 143 | 49 |  |  |  | 154 | 294 | 317 | 1242
Philippines | PHDR3 | Philippineskh.br.as.phl.17 | kh.br.as.phl.17 | Bangsamoro | 2028-07-22 | 2028-10-24 | Source Prep | Awaiting Source | - | 19.0667 | 36.6667 | 39.2 | 154.2667 |  | 143 | 259 | 16 | 162 | 7 | 39 | 38 | 36 | 12 | 2 | 322 | 415 | 165 |  |  | 0 | 61 | 3 | 11 | 133 | 45 |  |  |  | 143 | 275 | 294 | 1157
Philippines | PHDR3 | Philippineskh.br.as.phl.15 | kh.br.as.phl.15 | Soccskargen | 2028-07-28 | 2028-10-30 | Source Prep | Awaiting Source | - | 16.9333 | 32.2667 | 34.9333 | 136.1333 |  | 127 | 228 | 14 | 143 | 7 | 35 | 34 | 32 | 11 | 2 | 284 | 366 | 146 |  |  | 0 | 54 | 2 | 10 | 117 | 40 |  |  |  | 127 | 242 | 262 | 1021
Philippines | PHDR3 | Philippineskh.br.as.phl.16 | kh.br.as.phl.16 | Caraga | 2028-07-30 | 2028-11-02 | Source Prep | Awaiting Source | - | 10.8 | 20.8 | 22.4 | 87.8667 |  | 81 | 147 | 9 | 92 | 4 | 22 | 22 | 21 | 7 | 1 | 183 | 236 | 94 |  |  | 0 | 35 | 2 | 6 | 76 | 26 |  |  |  | 81 | 156 | 168 | 659
Philippines | PHDR3 | Philippineskh.br.as.phl.13 | kh.br.as.phl.13 | Northern Mindanao | 2028-08-05 | 2028-11-07 | Source Prep | Awaiting Source | - | 19.4667 | 37.2 | 40 | 156.8 |  | 146 | 263 | 16 | 164 | 8 | 40 | 39 | 37 | 12 | 2 | 327 | 422 | 168 |  |  | 0 | 62 | 3 | 11 | 135 | 46 |  |  |  | 146 | 279 | 300 | 1176
Philippines | PHDR3 | Philippineskh.br.as.phl.14 | kh.br.as.phl.14 | Davao | 2028-08-11 | 2028-11-13 | Source Prep | Awaiting Source | - | 20.2667 | 38.8 | 41.7333 | 163.6 |  | 152 | 274 | 17 | 172 | 8 | 41 | 41 | 38 | 13 | 2 | 342 | 440 | 175 |  |  | 0 | 65 | 3 | 11 | 141 | 48 |  |  |  | 152 | 291 | 313 | 1227
Philippines | PHDR3 | Philippineskh.br.as.phl.12 | kh.br.as.phl.12 | Zamboanga Peninsula | 2028-08-13 | 2028-11-16 | Source Prep | Awaiting Source | - | 14.9333 | 28.6667 | 30.8 | 120.8 |  | 112 | 203 | 12 | 127 | 6 | 31 | 30 | 28 | 9 | 2 | 252 | 325 | 129 |  |  | 0 | 48 | 2 | 8 | 104 | 36 |  |  |  | 112 | 215 | 231 | 906

## Monthly Inventory (hidden)
COUNTRY | DR | Combination | BR_ID | BR_Name | Driven Km | Naming QA | DC2 | Finishing | Source Prep | HLA | ADC | MPRA | FinIshing | PDS | DC2 | Finishing | Month & Year | Naming QA Inventory | DC2 Inventory | Source Prep | Finishing |  |  |  | COUNTRY | BR_ID | BR_Name | 3DV Processing End Date | 3DV Processing Status | 3DV Processing End Date | Pre-HLA Effort | Holiday List
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_A | kh.br.sa.bra.08_A | São Paulo | 34714 | 2025-12-31 | 2026-06-20 |  | 0 | 0 | 0 | 10 |  | Dec'25 | Jun'26 |  | Jan'26 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.01 | Mumbai | 2024-06-22 | Completed | Jun'24 | #N/A | 2025-01-01
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_C | kh.br.sa.bra.08_C | Campinas | 23453 | 2026-01-07 | 2026-08-09 |  | 0 | 0 | 0 | 1181.8667 |  | Jan'26 | Aug'26 |  | Feb'26 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.02 | Pune | 2024-07-12 | Completed | Jul'24 | #N/A | 2025-01-14
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_D | kh.br.sa.bra.08_D | Ribeirão Preto | 23151 | 2026-01-19 | 2026-09-06 |  | 0 | 0 | 0 | 1890.8 |  | Jan'26 | Sep'26 |  | Mar'26 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.05 | Indore | 2024-07-30 | Completed | Jul'24 | #N/A | 2025-03-14
Brazil_P2 | BRDRSP | Brazil_P2kh.br.sa.bra.08_B | kh.br.sa.bra.08_B | São José dos Campos | 26018 | 2026-01-27 | 2026-09-18 |  | 0 | 0 | 0 | 1996.9333 |  | Jan'26 | Sep'26 |  | Apr'26 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.03 | Nanded | 2024-08-15 | Completed | Aug'24 | #N/A | 2025-03-31
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_A | kh.br.sa.bra.11_A | Rio de Janeiro | 14299 | 2026-01-29 | 2026-07-07 |  | 0 | 0 | 0 | 479.0667 |  | Jan'26 | Jul'26 |  | May'26 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.04 | Nagpur | 2024-08-28 | Completed | Aug'24 | #N/A | 2025-04-18
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_B | kh.br.sa.bra.11_B | Campos dos Goytacazes | 18163 | 2026-01-31 | 2026-07-12 |  | 0 | 0 | 0 | 1110.5333 |  | Jan'26 | Jul'26 |  | Jun'26 | 0 | 10 | 0 | 0 |  |  |  | India | kh.br.as.ind.06 | Jabalpur | 2024-08-14 | Completed | Aug'24 | #N/A | 2025-05-01
Brazil_P2 | BRDRRIO | Brazil_P2kh.br.sa.bra.11_C | kh.br.sa.bra.11_C | Vitória | 7469 | 2026-02-06 | 2026-07-21 |  | 0 | 0 | 0 | 575.2 |  | Feb'26 | Jul'26 |  | Jul'26 | 1143.4667 | 2164.8 | 0 | 0 |  |  |  | India | kh.br.as.ind.11 | Warangal | 2024-08-06 | Completed | Aug'24 | #N/A | 2025-06-02
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.16 | kh.br.sa.bra.16 | Salvador | 23933 | 2026-02-22 | 2026-10-04 |  | 0 | 0 | 0 | 1507.0667 |  | Feb'26 | Oct'26 |  | Aug'26 | 316.5333 | 1181.8667 | 0 | 0 |  |  |  | India | kh.br.as.ind.07 | Goa | 2024-09-04 | Completed | Sep'24 | #N/A | 2025-08-15
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.17 | kh.br.sa.bra.17 | Recife | 22668 | 2026-03-10 | 2026-10-12 |  | 0 | 0 | 0 | 1014.4 |  | Mar'26 | Oct'26 |  | Sep'26 | 342.6667 | 3887.7333 | 0 | 0 |  |  |  | India | kh.br.as.ind.08 | Davanagere | 2024-08-10 | Completed | Aug'24 | #N/A | 2025-08-27
Brazil_P2 | BRDRNE | Brazil_P2kh.br.sa.bra.18 | kh.br.sa.bra.18 | Natal | 14335 | 2026-04-02 | 2026-10-21 |  | 0 | 0 | 0 | 568.4 |  | Apr'26 | Oct'26 |  | Oct'26 | 1271.0667 | 3627.7333 | 0 | 0 |  |  |  | India | kh.br.as.ind.09 | Bengaluru | 2024-09-04 | Completed | Sep'24 | #N/A | 2025-12-25
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.13 | kh.br.sa.bra.13 | Sao Luis | 11777 | 2026-03-23 | 2026-10-25 |  | 0 | 0 | 0 | 304.8 |  | Mar'26 | Oct'26 |  | Nov'26 | 978 | 3444.6667 | 0 | 0 |  |  |  | India | kh.br.as.ind.10 | Hyderabad | 2024-09-27 | Completed | Sep'24 | #N/A | 2025-10-02
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.14 | kh.br.sa.bra.14 | Teresina | 8173 | 2026-03-24 | 2026-10-28 |  | 0 | 0 | 0 | 233.0667 |  | Mar'26 | Oct'26 |  | Dec'26 | 0 | 2709.2 | 0 | 0 |  |  |  | India | kh.br.as.ind.12 | Kadapa | 2024-12-04 | Completed | Dec'24 | #N/A | 2026-01-14
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.15 | kh.br.sa.bra.15 | Fortaleza | 15472 | 2026-04-23 | 2026-11-07 |  | 0 | 0 | 0 | 582.6667 |  | Apr'26 | Nov'26 |  | Jan'27 | 0 | 4431.8667 | 0 | 0 |  |  |  | India | kh.br.as.ind.13 | Vijayawada | 2024-11-05 | Completed | Nov'24 | #N/A | 2025-10-20
Brazil_P2 | BRDRN | Brazil_P2kh.br.sa.bra.12 | kh.br.sa.bra.12 | Palmas | 6544 | 2026-05-06 | 2026-11-12 |  | 0 | 0 | 0 | 115.8667 |  | May'26 | Nov'26 |  | Feb'27 | 0 | 4189.2 | 0 | 0 |  |  |  | India | kh.br.as.ind.20 | Bikaner | 2024-11-06 | Completed | Nov'24 | #N/A | 2026-01-01
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.10_B | kh.br.sa.bra.10_B | Uberlândia | 24034 | 2026-03-17 | 2026-11-28 |  | 0 | 0 | 0 | 2746.1333 |  | Mar'26 | Nov'26 |  | Mar'27 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.19 | Mahesana | 2024-12-07 | Completed | Dec'24 | #N/A | 2026-03-14
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.10_A | kh.br.sa.bra.10_A | Belo Horizonte | 18327 | 2026-05-13 | 2026-12-13 |  | 0 | 0 | 0 | 1369.3333 |  | May'26 | Dec'26 |  | Apr'27 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.18 | Bhavnagar | 2024-12-31 | Completed | Dec'24 | #N/A | 2026-03-31
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.09_B | kh.br.sa.bra.09_B | Goiânia | 27365 | 2026-06-28 | 2026-12-27 |  | 0 | 0 | 0 | 1339.8667 |  | Jun'26 | Dec'26 |  | May'27 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.21 | Ajmer | 2024-12-19 | Completed | Dec'24 | #N/A | 2026-04-18
Brazil_P2 | BRDRC_A | Brazil_P2kh.br.sa.bra.09_A | kh.br.sa.bra.09_A | Brasília | 8952 | 2026-07-09 | 2027-01-02 |  | 0 | 0 | 0 | 548.1333 |  | Jul'26 | Jan'27 |  | Jun'27 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.22 | Jaipur | 2025-01-11 | Completed | Jan'25 | #N/A | 2026-05-01
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.07_A | kh.br.sa.bra.07_A | Curitiba | 28875 | 2026-10-17 | 2027-01-17 |  | 0 | 86.5333 | 1184.5333 | 1969.6 |  | Oct'26 | Jan'27 |  | Jul'27 | 202.5333 | 0 | 31.6 | 0 |  |  |  | India | kh.br.as.ind.26 | Dehradun | 2025-01-28 | Completed | Jan'25 | #N/A | 2026-06-02
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.06 | kh.br.sa.bra.06 | Porto Alegre | 24358 | 2026-07-30 | 2027-01-27 |  | 0 | 0 | 1143.4667 | 1914.1333 |  | Jul'26 | Jan'27 |  | Aug'27 | 346.1333 | 0 | 54 | 0 |  |  |  | India | kh.br.as.ind.23 | Delhi | 2025-03-01 | Completed | Mar'25 | #N/A | 2026-08-27
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.05 | kh.br.sa.bra.05 | Corumba | 12741 | 2026-08-11 | 2027-02-01 |  | 0 | 0 | 0 | 549.8667 |  | Aug'26 | Feb'27 |  | Sep'27 | 1701.3333 | 0 | 265.7333 | 0 |  |  |  | India | kh.br.as.ind.24 | Haryāna | 2025-03-15 | Completed | Mar'25 | #N/A | 2026-08-15
Brazil_P2 | BRDRS_A | Brazil_P2kh.br.sa.bra.07_B | kh.br.sa.bra.07_B | Joinville | 16540 | 2026-11-24 | 2027-02-09 |  | 0 | 246 | 732 | 1124.8 |  | Nov'26 | Feb'27 |  | Oct'27 | 1502 | 0 | 234.5333 | 0 |  |  |  | India | kh.br.as.ind.25 | Jalandhar | 2025-05-13 | Planned | May'25 | #N/A | 2026-10-02
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.04 | kh.br.sa.bra.04 | Cuiaba | 13464 | 2026-08-19 | 2027-02-16 |  | 0 | 0 | 316.5333 | 872.6667 |  | Aug'26 | Feb'27 |  | Nov'27 | 1202.1333 | 81.0667 | 187.8667 | 0 |  |  |  | India | kh.br.as.ind.35 | Lakshadweep | 2025-03-04 | Skipped | Mar'25 | #N/A | 2026-10-20
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.01 | kh.br.sa.bra.01 | Porto Velho | 5848 | 2026-08-25 | 2027-02-17 |  | 0 | 0 | 0 | 389.3333 |  | Aug'26 | Feb'27 |  | Dec'27 | 412 | 138.2667 | 64.4 | 0 |  |  |  | India | kh.br.as.ind.17 | Chennai | 2024-10-08 | Completed | Oct'24 | #N/A | 2026-12-25
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.03 | kh.br.sa.bra.03 | Belem | 8948 | 2026-09-07 | 2027-02-19 |  | 0 | 229.4667 | 95.7333 | 740.5333 |  | Sep'26 | Feb'27 |  | Jan'28 | 968.2667 | 679.4667 | 151.2 | 0 |  |  |  | India | kh.br.as.ind.15 | Madurai | 2024-11-05 | Completed | Nov'24 | #N/A
Brazil_P2 | BRDRW | Brazil_P2kh.br.sa.bra.02 | kh.br.sa.bra.02 | Manaus | 13424 | 2026-09-11 | 2027-02-19 |  | 0 | 0 | 17.4667 | 512 |  | Sep'26 | Feb'27 |  | Feb'28 | 1024.6667 | 255.2 | 160 | 0 |  |  |  | India | kh.br.as.ind.16 | Erode | 2024-11-16 | Completed | Nov'24 | #N/A
Indonesia | IDDRSM | Indonesiakh.br.as.idn.01 | kh.br.as.idn.01 | Aceh | 7632.6119 | 2027-07-26 | 2027-11-28 |  | 31.6 | 90.1333 | 112.4 | 81.0667 |  | Jul'27 | Nov'27 |  | Mar'28 | 1262.9333 | 345.3333 | 202 | 0 |  |  |  | India | kh.br.as.ind.14 | Kerala | 2025-05-05 | Planned | May'25 | #N/A
Indonesia | IDDRSM | Indonesiakh.br.as.idn.05 | kh.br.as.idn.05 | Lampung | 11419.8559 | 2027-08-28 | 2027-12-18 |  | 54 | 154 | 192.1333 | 138.2667 |  | Aug'27 | Dec'27 |  | Apr'28 | 1459.3333 | 480.5333 | 228 | 0 |  |  |  | India | kh.br.as.ind.36 | Andaman and Nicobar Islands | 2025-05-22 | Planned | May'25 | #N/A
Indonesia | IDDRSM | Indonesiakh.br.as.idn.04 | kh.br.as.idn.04 | Sumatra Island South | 21126.6364 | 2027-09-09 | 2028-01-02 |  | 92.9333 | 264.6667 | 330.4 | 237.4667 |  | Sep'27 | Jan'28 |  | May'28 | 525.2 | 551.6 | 112.2667 | 0 |  |  |  | India | kh.br.as.ind.40 | Jammu and Kashmīr Central | 2025-03-07 | Skipped | Mar'25 | #N/A
Indonesia | IDDRSM | Indonesiakh.br.as.idn.03 | kh.br.as.idn.03 | Sumatra Island Central | 20891.2863 | 2027-09-21 | 2028-01-14 |  | 84 | 239.0667 | 298.5333 | 214.8 |  | Sep'27 | Jan'28 |  | Jun'28 | 689.3333 | 671.7333 | 173.7333 | 0 |  |  |  | India | kh.br.as.ind.41 | Jammu and Kashmīr East | 2025-03-12 | Skipped | Mar'25 | #N/A
Indonesia | IDDRSM | Indonesiakh.br.as.idn.02 | kh.br.as.idn.02 | Medan | 17053.2041 | 2027-09-29 | 2028-01-28 |  | 88.8 | 252.9333 | 315.7333 | 227.2 |  | Sep'27 | Jan'28 |  | Jul'28 | 724.9333 | 710.8 | 182.4 | 0 |  |  |  | India | kh.br.as.ind.39 | Jammu and Kashmīr West | 2025-03-04 | Skipped | Mar'25 | #N/A
Indonesia | IDDRKA | Indonesiakh.br.as.idn.07 | kh.br.as.idn.07 | West Kalimantan | 24285.3839 | 2027-10-03 | 2028-02-11 |  | 48.5333 | 138.1333 | 172.4 | 124.1333 |  | Oct'27 | Feb'28 |  | Aug'28 | 217.2 | 717.7333 | 54.6667 | 0 |  |  |  | India | kh.br.as.ind.42 | Jammu and Kashmīr North | 2025-03-11 | Skipped | Mar'25 | #N/A
Indonesia | IDDRKA | Indonesiakh.br.as.idn.06 | kh.br.as.idn.06 | East Kalimantan | 19072.7125 | 2027-10-06 | 2028-02-22 |  | 51.2 | 146 | 182.2667 | 131.0667 |  | Oct'27 | Feb'28 |  | Sep'28 | 0 | 1607.7333 | 0 | 0 |  |  |  | India | kh.br.as.ind.44 | Aksai Chin | 2025-04-02 | Skipped | Apr'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.09 | kh.br.as.idn.09 | Jakarta | 3670.6587 | 2027-10-14 | 2028-03-03 |  | 63.3333 | 180.5333 | 225.3333 | 162.2667 |  | Oct'27 | Mar'28 |  | Oct'28 | 0 | 1385.6 | 0 | 0 |  |  |  | India | kh.br.as.ind.50 | Susta | 2024-12-19 | Skipped | Dec'24 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.08 | kh.br.as.idn.08 | Banten | 7393.3955 | 2027-10-24 | 2028-03-23 |  | 71.4667 | 203.4667 | 253.8667 | 183.0667 |  | Oct'27 | Mar'28 |  | Nov'28 | 0 | 529.0667 | 0 | 0 |  |  |  | India | kh.br.as.ind.29 | Varanasi | 2025-03-07 | Completed | Mar'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_A | kh.br.as.idn.10_A | West Java A | 11005.7701 | 2027-11-12 | 2028-04-08 |  | 103.6 | 294.9333 | 368 | 265.0667 |  | Nov'27 | Apr'28 |  | Dec'28 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.27 | Agra | 2025-03-27 | Completed | Mar'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_C | kh.br.as.idn.12_C | East Java C | 13706.3789 | 2027-11-29 | 2028-04-24 |  | 84.2667 | 239.8667 | 299.3333 | 215.4667 |  | Nov'27 | Apr'28 |  | Jan'29 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.28 | Lucknow | 2025-05-13 | Planned | May'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_C | kh.br.as.idn.11_C | Yogyakarta | 13092.8417 | 2027-12-17 | 2028-05-07 |  | 64.4 | 183.3333 | 228.6667 | 164.5333 |  | Dec'27 | May'28 |  | Feb'29 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.30 | Patna | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_B | kh.br.as.idn.12_B | East Java B | 11238.8128 | 2028-01-07 | 2028-05-18 |  | 83.3333 | 237.4667 | 296.2667 | 213.4667 |  | Jan'28 | May'28 |  | Mar'29 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.46 | Chumar | 2025-03-04 | Skipped | Mar'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_B | kh.br.as.idn.11_B | Central Java B | 9545.187 | 2028-01-23 | 2028-05-28 |  | 67.8667 | 193.2 | 241.3333 | 173.6 |  | Jan'28 | May'28 |  | Apr'29 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.37 | Ladākh | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.12_A | kh.br.as.idn.12_A | East Java A | 11006.766 | 2028-02-08 | 2028-06-10 |  | 76.4 | 217.6 | 271.7333 | 195.4667 |  | Feb'28 | Jun'28 |  | May'29 | 0 | 0 | 0 | 0 |  |  |  | India | kh.br.as.ind.45 | Demchok | 2025-04-23 | Skipped | Apr'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_C | kh.br.as.idn.10_C | West Java C | 9856.5905 | 2028-02-22 | 2028-06-20 |  | 83.6 | 238.1333 | 297.2 | 213.8667 |  | Feb'28 | Jun'28 |  | Overall | 16289.7333 | 33801.2 | 2102.4 | 0 |  |  |  | India | kh.br.as.ind.51 | Arunāchal Pradesh | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.10_B | kh.br.as.idn.10_B | West Java B | 9493.5621 | 2028-03-08 | 2028-06-30 |  | 102.5333 | 292 | 364.4 | 262.4 |  | Mar'28 | Jun'28 | [9 empty] | India | kh.br.as.ind.48 | Lapthal | 2025-06-17 | Skipped | Jun'25 | #N/A
Indonesia | IDDRJW | Indonesiakh.br.as.idn.11_A | kh.br.as.idn.11_A | Central Java A | 8464.8366 | 2028-03-23 | 2028-07-09 |  | 86.9333 | 247.7333 | 309.0667 | 222.5333 |  | Mar'28 | Jul'28 |  |  | TRUE | TRUE | TRUE |  |  |  |  | India | kh.br.as.ind.49 | Limpiyadhura | 2025-06-17 | Skipped | Jun'25 | #N/A
Indonesia | IDDRSL | Indonesiakh.br.as.idn.14 | kh.br.as.idn.14 | Celebes South | 19403.9646 | 2028-04-07 | 2028-07-21 |  | 78.6667 | 224.1333 | 279.6 | 201.3333 |  | Apr'28 | Jul'28 | [9 empty] | India | kh.br.as.ind.47 | Shipki | 2025-05-14 | Planned | May'25 | #N/A
Indonesia | IDDRSL | Indonesiakh.br.as.idn.13 | kh.br.as.idn.13 | Celebes North | 9176.757 | 2028-04-11 | 2028-07-24 |  | 40.6667 | 115.8667 | 144.5333 | 104.1333 |  | Apr'28 | Jul'28 | [9 empty] | India | kh.br.as.ind.38 | Jammu and Kashmīr South | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRNU | Indonesiakh.br.as.idn.16 | kh.br.as.idn.16 | East Nusa Tenggara | 10516.7618 | 2028-04-17 | 2028-07-29 |  | 32 | 91.0667 | 113.6 | 82 |  | Apr'28 | Jul'28 | [9 empty] | India | kh.br.as.ind.31 | Ranchi | 2024-12-19 | Completed | Dec'24 | #N/A
Indonesia | IDDRNU | Indonesiakh.br.as.idn.15 | kh.br.as.idn.15 | Bali | 9142.3823 | 2028-04-27 | 2028-08-04 |  | 57.8667 | 164.8 | 205.6 | 147.8667 |  | Apr'28 | Aug'28 | [9 empty] | India | kh.br.as.ind.33 | Kolkata | 2025-03-01 | Completed | Mar'25 | #N/A
Indonesia | IDDRML | Indonesiakh.br.as.idn.18 | kh.br.as.idn.18 | North Maluku | 3589.092 | 2028-04-28 | 2028-08-05 |  | 7.7333 | 21.8667 | 27.3333 | 20 |  | Apr'28 | Aug'28 | [9 empty] | India | kh.br.as.ind.34 | Dimapur | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRML | Indonesiakh.br.as.idn.17 | kh.br.as.idn.17 | Maluku | 4499.7502 | 2028-04-29 | 2028-08-06 |  | 11.0667 | 31.6 | 39.3333 | 28.2667 |  | Apr'28 | Aug'28 | [9 empty] | India | kh.br.as.ind.32 | Sambalpur | 2025-06-11 | Planned | Jun'25 | #N/A
Indonesia | IDDRPP | Indonesiakh.br.as.idn.20 | kh.br.as.idn.20 | Papua East | 6725.8425 | 2028-05-01 | 2028-08-08 |  | 17.4667 | 49.8667 | 62.2667 | 44.6667 |  | May'28 | Aug'28
Indonesia | IDDRPP | Indonesiakh.br.as.idn.19 | kh.br.as.idn.19 | Papua West | 6988.9587 | 2028-05-03 | 2028-08-10 |  | 15.2 | 43.2 | 53.8667 | 38.8 |  | May'28 | Aug'28 |  | Month | Naming Inventory (In Mandays) | DC2 Inventory (In Mandays) | Source Prep Inventory (basis PDS date) | Finishing | Month & Year | Naming KM | DC2 KM
Philippines | PHDR2 | Philippineskh.br.as.phl.08 | kh.br.as.phl.08 | Mimaropa | 8940.6126 | 2028-03-26 | 2028-07-13 |  | 12.5333 | 23.8667 | 25.8667 | 100.8 |  | Mar'28 | Jul'28 |  | Sep'26 | 1802.6667 | 7244.4 | 0 | 0 | Sep'26 | 22372 | 49169
Philippines | PHDR2 | Philippineskh.br.as.phl.09 | kh.br.as.phl.09 | Western Visayas | 7945.4468 | 2028-05-07 | 2028-08-14 |  | 18.2667 | 34.9333 | 37.6 | 147.6 |  | May'28 | Aug'28 |  | Oct'26 | 1271.0667 | 3627.7333 | 0 | 0 | Oct'26 | 28875 | 80886
Philippines | PHDR2 | Philippineskh.br.as.phl.18 | kh.br.as.phl.18 | Negros Island | 9294.4172 | 2028-05-12 | 2028-08-20 |  | 18.4 | 35.2 | 38 | 148.6667 |  | May'28 | Aug'28 |  | Nov'26 | 978 | 3444.6667 | 0 | 0 | Nov'26 | 16540 | 46050
Philippines | PHDR2 | Philippineskh.br.as.phl.11 | kh.br.as.phl.11 | Eastern Visayas | 6975.1976 | 2028-05-15 | 2028-08-23 |  | 17.6 | 33.6 | 36.1333 | 141.8667 |  | May'28 | Aug'28 |  | Dec'26 | 0 | 2709.2 | 0 | 0 | Dec'26 | 0 | 45692
Philippines | PHDR2 | Philippineskh.br.as.phl.10 | kh.br.as.phl.10 | Central Visayas | 8945.6474 | 2028-05-24 | 2028-09-03 |  | 25.3333 | 48.4 | 52.1333 | 204.4 |  | May'28 | Sep'28 |  | Jan'27 | 0 | 4431.8667 | 0 | 0 | Jan'27 | 0 | 62185
Philippines | PHDR1 | Philippineskh.br.as.phl.06 | kh.br.as.phl.06 | Manila | 4315.9357 | 2028-06-04 | 2028-09-11 |  | 78.2667 | 149.6 | 160.8 | 631.6 |  | Jun'28 | Sep'28 |  | Feb'27 | 0 | 4189.2 | 0 | 0 | Feb'27 | 0 | 70965
Philippines | PHDR1 | Philippineskh.br.as.phl.07 | kh.br.as.phl.07 | Bicol | 6904.7119 | 2028-06-09 | 2028-09-13 |  | 23.4667 | 44.9333 | 48.2667 | 189.8667 |  | Jun'28 | Sep'28 |  | Mar'27 | 0 | 0 | 0 | 0 | Mar'27 | 0 | 0
Philippines | PHDR1 | Philippineskh.br.as.phl.04 | kh.br.as.phl.04 | Central Luzon | 15235.0521 | 2028-06-22 | 2028-09-28 |  | 72 | 137.7333 | 148 | 581.8667 |  | Jun'28 | Sep'28 |  | Apr'27 | 0 | 0 | 0 | 0 | Apr'27 | 0 | 0
Philippines | PHDR1 | Philippineskh.br.as.phl.05 | kh.br.as.phl.05 | Calabarzon | 14445.8084 | 2028-07-10 | 2028-10-14 |  | 93.8667 | 179.6 | 193.2 | 758.4 |  | Jul'28 | Oct'28 |  | May'27 | 0 | 0 | 0 | 0 | May'27 | 0 | 0
Philippines | PHDR1 | Philippineskh.br.as.phl.02 | kh.br.as.phl.02 | Cordillera | 4142.3365 | 2028-07-11 | 2028-10-15 |  | 6.9333 | 13.3333 | 14.2667 | 56 |  | Jul'28 | Oct'28 |  | Jun'27 | 0 | 0 | 0 | 0 | Jun'27 | 0 | 0
Philippines | PHDR1 | Philippineskh.br.as.phl.03 | kh.br.as.phl.03 | Cagayan Valley | 8833.822 | 2028-07-14 | 2028-10-19 |  | 14.2667 | 27.3333 | 29.4667 | 115.2 |  | Jul'28 | Oct'28 |  | Jul'27 | 202.5333 | 0 | 31.6 | 0 | Jul'27 | 7632.6119 | 0
Philippines | PHDR1 | Philippineskh.br.as.phl.01 | kh.br.as.phl.01 | Ilocos | 7974.7425 | 2028-07-20 | 2028-10-23 |  | 20.5333 | 39.2 | 42.2667 | 165.6 |  | Jul'28 | Oct'28 |  | Aug'27 | 346.1333 | 0 | 54 | 0 | Aug'27 | 11419.8559 | 0
Philippines | PHDR3 | Philippineskh.br.as.phl.17 | kh.br.as.phl.17 | Bangsamoro | 3307.8803 | 2028-07-22 | 2028-10-24 |  | 19.0667 | 36.6667 | 39.2 | 154.2667 |  | Jul'28 | Oct'28 |  | Sep'27 | 1701.3333 | 0 | 265.7333 | 0 | Sep'27 | 59071.1268 | 0
Philippines | PHDR3 | Philippineskh.br.as.phl.15 | kh.br.as.phl.15 | Soccskargen | 10514.3085 | 2028-07-28 | 2028-10-30 |  | 16.9333 | 32.2667 | 34.9333 | 136.1333 |  | Jul'28 | Oct'28 |  | Oct'27 | 1502 | 0 | 234.5333 | 0 | Oct'27 | 54422.1507 | 0
Philippines | PHDR3 | Philippineskh.br.as.phl.16 | kh.br.as.phl.16 | Caraga | 4840.8377 | 2028-07-30 | 2028-11-02 |  | 10.8 | 20.8 | 22.4 | 87.8667 |  | Jul'28 | Nov'28 |  | Nov'27 | 1202.1333 | 81.0667 | 187.8667 | 0 | Nov'27 | 24712.149 | 7632.6119
Philippines | PHDR3 | Philippineskh.br.as.phl.13 | kh.br.as.phl.13 | Northern Mindanao | 10575.0029 | 2028-08-05 | 2028-11-07 |  | 19.4667 | 37.2 | 40 | 156.8 |  | Aug'28 | Nov'28 |  | Dec'27 | 412 | 138.2667 | 64.4 | 0 | Dec'27 | 13092.8417 | 11419.8559
Philippines | PHDR3 | Philippineskh.br.as.phl.14 | kh.br.as.phl.14 | Davao | 11205.2023 | 2028-08-11 | 2028-11-13 |  | 20.2667 | 38.8 | 41.7333 | 163.6 |  | Aug'28 | Nov'28 |  | Jan'28 | 968.2667 | 679.4667 | 151.2 | 0 | Jan'28 | 20783.9998 | 59071.1268
Philippines | PHDR3 | Philippineskh.br.as.phl.12 | kh.br.as.phl.12 | Zamboanga Peninsula | 5603.0375 | 2028-08-13 | 2028-11-16 |  | 14.9333 | 28.6667 | 30.8 | 120.8 |  | Aug'28 | Nov'28 |  | Feb'28 | 1024.6667 | 255.2 | 160 | 0 | Feb'28 | 20863.3565 | 43358.0965
[17 empty] | Mar'28 | 1262.9333 | 345.3333 | 202 | 0 | Mar'28 | 26899.0113 | 11064.0543
[17 empty] | Apr'28 | 1459.3333 | 480.5333 | 228 | 0 | Apr'28 | 56328.7079 | 24712.149
[17 empty] | May'28 | 525.2 | 551.6 | 112.2667 | 0 | May'28 | 46875.5103 | 33876.8414
[17 empty] | Jun'28 | 689.3333 | 671.7333 | 173.7333 | 0 | Jun'28 | 26455.6997 | 30356.9186
[17 empty] | Jul'28 | 724.9333 | 710.8 | 182.4 | 0 | Jul'28 | 54059.7359 | 56502.9326
[17 empty] | Aug'28 | 217.2 | 717.7333 | 54.6667 | 0 | Aug'28 | 27383.2427 | 55161.0873
[17 empty] | Sep'28 | 0 | 1607.7333 | 0 | 0 | Sep'28 | 0 | 35401.3471
[17 empty] | Oct'28 | 0 | 1385.6 | 0 | 0 | Oct'28 | 0 | 49218.8982
[17 empty] | Nov'28 | 0 | 529.0667 | 0 | 0 | Nov'28 | 0 | 32224.0805
[17 empty] | Dec'28 | 0 | 0 | 0 | 0 | Dec'28 | 0 | 0
[17 empty] | Jan'29 | 0 | 0 | 0 | 0 | Jan'29 | 0 | 0
[17 empty] | Feb'29 | 0 | 0 | 0 | 0 | Feb'29 | 0 | 0
[17 empty] | Mar'29 | 0 | 0 | 0 | 0 | Mar'29 | 0 | 0
[17 empty] | Apr'29 | 0 | 0 | 0 | 0 | Apr'29 | 0 | 0
[17 empty] | May'29 | 0 | 0 | 0 | 0 | May'29 | 0 | 0
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | Month | Naming Inventory (In hours) | DC2 Inventory (In hours) | Source Prep Inventory (basis PDS date) | Finishing
[17 empty] | Sep'26 | 13520 | 54333 | 0 | 0
[17 empty] | Oct'26 | 9533 | 27208 | 0 | 0
[17 empty] | Nov'26 | 7335 | 25835 | 0 | 0
[17 empty] | Dec'26 | 0 | 20319 | 0 | 0
[17 empty] | Jan'27 | 0 | 33239 | 0 | 0
[17 empty] | Feb'27 | 0 | 31419 | 0 | 0
[17 empty] | Mar'27 | 0 | 0 | 0 | 0
[17 empty] | Apr'27 | 0 | 0 | 0 | 0
[17 empty] | May'27 | 0 | 0 | 0 | 0
[17 empty] | Jun'27 | 0 | 0 | 0 | 0
[17 empty] | Jul'27 | 1519 | 0 | 237 | 0
[17 empty] | Aug'27 | 2596 | 0 | 405 | 0
[17 empty] | Sep'27 | 12760 | 0 | 1993 | 0
[17 empty] | Oct'27 | 11265 | 0 | 1759 | 0
[17 empty] | Nov'27 | 9016 | 608 | 1409 | 0
[17 empty] | Dec'27 | 3090 | 1037 | 483 | 0
[17 empty] | Jan'28 | 7262 | 5096 | 1134 | 0
[17 empty] | Feb'28 | 7685 | 1914 | 1200 | 0
[17 empty] | Mar'28 | 9472 | 2590 | 1515 | 0
[17 empty] | Apr'28 | 10945 | 3604 | 1710 | 0
[17 empty] | May'28 | 3939 | 4137 | 842 | 0
[17 empty] | Jun'28 | 5170 | 5038 | 1303 | 0
[17 empty] | Jul'28 | 5437 | 5331 | 1368 | 0
[17 empty] | Aug'28 | 1629 | 5383 | 410 | 0
[17 empty] | Sep'28 | 0 | 12058 | 0 | 0
[17 empty] | Oct'28 | 0 | 10392 | 0 | 0
[17 empty] | Nov'28 | 0 | 3968 | 0 | 0
[17 empty] | Dec'28 | 0 | 0 | 0 | 0
[17 empty] | Jan'29 | 0 | 0 | 0 | 0
[17 empty] | Feb'29 | 0 | 0 | 0 | 0
[17 empty] | Mar'29 | 0 | 0 | 0 | 0
[17 empty] | Apr'29 | 0 | 0 | 0 | 0
[17 empty] | May'29 | 0 | 0 | 0 | 0
[17 empty] | 0 | 0 | 0 | 0 | 0